## Sheet1
American River Campus - Master Plan Update
Potential Project Matrix
09.20.2018
| Description | Objective | Opportunities | Constraints | Desired Location
Project | General description of the project. | What campus benefit is gained through the completion of the project? | What other positive impacts are possible with the project? | What is, or would, keep the project from happening? (Other than funding.) | Where on campus should the project be located? Should it be near like uses or programs?
Technical Education/Vocation | Modernization of existing buildings and spaces. | Provide the department with modernization improvements and potentially replace the old portable buildings. | Improve the north edge of the campus and entryway from the north parking lot. |  | Current Location.
Corporation Yard | Relocation of current corporation yard uses to the south end of the campus, as identified in the 2012 Master Plan. | Create additional area on which new instructional space may be developed at the front of campus adjacent to the campus core. | Open up additional educational space within the heart of campus. Improve vehicular circulation and connectivity between parking areas along College Oak Drive. |  | South end of campus as identified in the 2012 Master Plan.
Davies Hall | Modernization of the current Davies Hall, identified as a replacement building in the 2012 Master Plan. | Replace dated classrooms and upgrade classroom technology for modern teaching practices. | Create a more appealing front door for the campus. To develop a significant open space at the south edge of the campus core, highlighting the original Ranch House on campus property. |  | Western edge of campus, as shown in the 2012 Campus Master Plan.
Administration Building | Modernization of existing administrative office and meeting spaces. | Update one of the oldest buildings on campus to provide modern office and meeting amenities and to improve the "front door" image. | Create a piece of a new student support/welcome center on campus. |  | Current Location.
Instructional Space II | New teaching space to provide for an expanded student population. | Create a new image for the science districts as well as address the formal library quad. | Improve connections between the Library area and new science courtyard/quad. |  | Dependent on the location of Science and other future buildings.
Science
Raef Hall
Fine Arts Building | Moderniztion of exisitng Art Classrooms: 501, 502, 503, 503A, 504, 508/509, and 510/511. | Replace outdated classrooms for the Art department. The need to promote classroom technology to access modern teaching practicess is not possible in these classrooms; the electrical, plumbing and basic structures need to be enhanced to improve access and the questionable compliance of ADA and OSHA safety regulations. Additionally the need for increased and safe instructional space for course specific programs such as ceramics, photography, sculpture and gallery management courses lack safe instructional space and storage. A new Kaneko Gallery with additional exhibit space, on-site storage for PAC and the gallery, a proper classroom, and dust-free framing room would be part of this project. | Create a modern, safe and welcoming space for the students and the public for the arts community on campus. The Kaneko Gallery and use of PAC is a focal source for the colleges' Gallery Mangement Certificate. |  | Current location - FAA area.
Stadium |  | T
??
??
??