## Sheet1
American River Campus - Master Plan Update
Potential Project Matrix
09.20.2018
| Description | Objective | Opportunities | Constraints | Desired Location
Project | General description of the project. | What campus benefit is gained through the completion of the project? | What other positive impacts are possible with the project? | What is, or would, keep the project from happening? (Other than funding.) | Where on campus should the project be located? Should it be near like uses or programs?
Technical Education/Vocation | Modernization of existing buildings and spaces. | Provide the department with modernization improvements and potentially replace the old portable buildings. | Improve the north edge of the campus and entryway from the north parking lot. |  | Current Location.
Corporation Yard | Relocation of current corporation yard uses to the south end of the campus, as identified in the 2012 Master Plan. | Create additional area on which new instructional space may be developed at the front of campus adjacent to the campus core. | Open up additional educational space within the heart of campus. Improve vehicular circulation and connectivity between parking areas along College Oak Drive. |  | South end of campus as identified in the 2012 Master Plan.
Davies Hall | Modernization of the current Davies Hall, identified as a replacement building in the 2012 Master Plan. | Replace dated classrooms and upgrade classroom technology for modern teaching practices. | Create a more appealing front door for the campus. To develop a significant open space at the south edge of the campus core, highlighting the original Ranch House on campus property. |  | Western edge of campus, as shown in the 2012 Campus Master Plan.
Administration Building | Modernization of existing administrative office and meeting spaces. | Update one of the oldest buildings on campus to provide modern office and meeting amenities and to improve the "front door" image. | Create a new student support/welcome center on campus. |  | Current Location.
Instructional Space II | New teaching space to provide for an expanded student population. | Create a new image for the science districts as well as address the formal library quad. | Improve connections between the Library area and new science courtyard/quad. |  | Dependent on the location of Science and other future buildings.
Science
Raef Hall
Fine Arts Building
Stadium
Parking
Parking (General) | Parking and sidewalk improvements: 1. Create well-defined, readily identifiable, student drop-off zones with good traffic flow on the north and south ends of campus. These drop-off zones should not conflict with fire lanes, pedestrian zones, or staff parking and should have adequate sidewalks and crosswalks. Ideally there should also be bus and paratransit stops next to the drop-off zones. 2. Add sidewalks to both sides of the street to the north end of the street that runs through the middle of campus. 3. Lower the double speedbumps in Lots B, C, and D so that they are friendly towards low-profile, low-emission vehicles. Also lower the crosswalk "hump" located at the north end of the street passing through campus. All new speed bumps should not be any higher than the "newer" ones located in the entrance to the Stadium Lot/Parking Garage | Improved accessibility, safety and traffic flow that will require less policing, and that is safe for all vehicles | Improved accessibility, safety and traffic flow that will require less policing. Improved traffic flow on surrounding neighborhood streets
Parking (General--continued from above) | 4. Add solar canopies to established permanent parking lots | Provide green energy for the college | Decrease the college's consumption of non-renewable resources |  | All established permanent parking lots
Parking (Near the Child Development Center) | 1. Enlarge the current Child Development Center's drop-off zone to include all parking spaces in front (to the south) of the Center. 2. To recoup the lost staff parking, add additional staff parking spaces to the east of the CDC building. Currently these areas are a gravel lot and some landscaping 3. In addition, add sidewalks to both sides of the street on streets surrounding the CDC and add a crosswalk for the street southeast of the CDC building. 4. If possible, move the fire hydrant that is in the middle of the disabled parking 10ft to the north so that it is in the landscaping, instead of in the middle of the parking lot | Increased parking, and improved safety and better traffic flow for the children, parents, staff and faculty who use the Child Development Center, or who park near the center. Currently traffic backs up during prime drop-off times and blocks the fire lane access. The fire hydrant in the parking lot has been crashed into several times, as evidenced by the bent safety poles that surround the hydrant. | Increased parking and improved safety and traffic flow that will require less policing |  | Current location and nearby undeveloped space to the east and southeast that can be turned into parking spaces
Signage | Campus buildings should have clear signs on all corners of the building. Also more weatherproof campus map/information stations need to be posted in common entrance areas to the college | Provide much-needed directions available to all on-campus users | Create a more welcoming and user-friendly environment for all |  | Current locations and new campus map/information stations added to the main entrance areas for the college
Bathrooms for STEM/New Buildings | STEM building bathrooms and all new bathrooms should be gender neutral, easily accessible, while maintaining privacy. The style of the bathrooms should minimize required maintenance: solid surfaces that minimize grout, paper towel dispensers that work without jamming, and please NO auto-flush toilets. Existing bathrooms could be modernized and made more accessible and gender neutral overtime. | Provide students, faculty and staff with equitable bathrooms that are easy to keep clean and maintain. | Create a more welcoming, equitable and clean environment for all |  | Current location
Bike Accessibility | Create a bike-friendly campus with adequate, clearly-marked bike lanes, and adequate, secure bike racks | Improve and reduce vehicle traffic and pollution, by encouraging alternate transportation. | Create a less-congested, less-polluted environment that encourages the use of alternative transportation. |  | Current locations and new locations TBD
Some general questions | Why is the student health center located in Admin? Can we address this in the modernization process? Is the location of the Admin building really the best place for a "Student Welcome Center"? Shouldn't e-services, admissions and records, business office, and financial aid all be located in the same building?
Some general suggestions | 1. Buildings do not need to match, but it would be nice if there were some common architectural details that provide some continuity. 2. Avoid the "Soviet-Era, Block-style" buildings as well as buildings similar in look to the old "liberal arts" buildings that are being demolished. 3. Create a variety of gathering/seating areas indoors and outdoors. Campus needs more covered outdoor areas, especially by the portables. Would be nice if covered areas used solar canopies. 4. Building designs should have exits and entrances that make sense with the flow of pedestrian traffic and current walkways