## Sheet1
American River Campus - Master Plan Update
Potential Project Matrix
09.20.2018
| Description | Objective | Opportunities | Constraints | Desired Location
Project | General description of the project. | What campus benefit is gained through the completion of the project? | What other positive impacts are possible with the project? | What is, or would, keep the project from happening? (Other than funding.) | Where on campus should the project be located? Should it be near like uses or programs?
Technical Education/Vocation | Modernization of existing buildings and spaces. | Provide the department with modernization improvements and potentially replace the old portable buildings. | Improve the north edge of the campus and entryway from the north parking lot. |  | Current Location.
Corporation Yard | Relocation of current corporation yard uses to the south end of the campus, as identified in the 2012 Master Plan. | Create additional area on which new instructional space may be developed at the front of campus adjacent to the campus core. | Open up additional educational space within the heart of campus. Improve vehicular circulation and connectivity between parking areas along College Oak Drive. |  | South end of campus as identified in the 2012 Master Plan.
Davies Hall | Modernization of the current Davies Hall, identified as a replacement building in the 2012 Master Plan. | Replace dated classrooms and upgrade classroom technology for modern teaching practices. | Create a more appealing front door for the campus. To develop a significant open space at the south edge of the campus core, highlighting the original Ranch House on campus property. |  | Western edge of campus, as shown in the 2012 Campus Master Plan.
Administration Building | Modernization of existing administrative office and meeting spaces. | Update one of the oldest buildings on campus to provide modern office and meeting amenities and to improve the "front door" image. | Create a piece of a new student support/welcome center on campus. |  | Current Location.
Instructional Space II | New teaching space to provide for an expanded student population. | Create a new image for the science districts as well as address the formal library quad. | Improve connections between the Library area and new science courtyard/quad. |  | Dependent on the location of Science and other future buildings.
Science | Modernization of science buildings to enhance the quality of lab spaces and student experience. Current facility is plagued with issues ranging from leaking roofs to building design and use issues. Over 100 maintenance issues with 20% being major maintenance issues in suspense. Building is 60 years old and cannot support 21st century scientific equipment and needs. | Modernize the building and laboratory spaces to meet 21st century laboratory standards and needs, improve health and safety, and hollistically improve student learning experience through meaningful space design and flow. | To centralize the STEM fields in one area on campus to foster interdisciplinary interaction and learning. The STEM buildings would serve to advertise to the community ARC's leadership and commitment to train future students in STEM careers. |  | As a new building that connects to STEM I building to centralize the STEM fields
Raef Hall
Fine Arts Building
Stadium
??
??
??