## Sheet1
American River Campus - Master Plan Update
Potential Project Matrix
09.20.2018
| Description | Objective | Opportunities | Constraints | Desired Location
Project | General description of the project. | What campus benefit is gained through the completion of the project? | What other positive impacts are possible with the project? | What is, or would, keep the project from happening? (Other than funding.) | Where on campus should the project be located? Should it be near like uses or programs?
Technical Education/Vocation | Modernization of existing buildings and spaces. | Provide the department with modernization improvements and potentially replace the old portable buildings. | Improve the north edge of the campus and entryway from the north parking lot. |  | Current Location.
Corporation Yard | Relocation of current corporation yard uses to the south end of the campus, as identified in the 2012 Master Plan. | Create additional area on which new instructional space may be developed at the front of campus adjacent to the campus core. | Open up additional educational space within the heart of campus. Improve vehicular circulation and connectivity between parking areas along College Oak Drive. |  | South end of campus as identified in the 2012 Master Plan.
Davies Hall | Modernization of the current Davies Hall, identified as a replacement building in the 2012 Master Plan. (Project cannot be done without Corp Yard) | Replace dated classrooms and upgrade classroom technology for modern teaching practices. | Create a more appealing front door for the campus. To develop a significant open space at the south edge of the campus core, highlighting the original Ranch House on campus property. |  | Western edge of campus, as shown in the 2012 Campus Master Plan.
Administration Building | Modernization of existing administrative office and meeting spaces. | Update one of the oldest buildings on campus to provide modern office and meeting amenities and to improve the "front door" image. | Create a piece of a new student support/welcome center on campus. | Near future adjustments in building move this option lower on our list. | Current Location.
Instructional Space II | New teaching space to provide for an expanded student population. | Create a new image for the science districts as well as address the formal library quad. | Improve connections between the Library area and new science courtyard/quad. |  | Dependent on the location of Science and other future buildings.
Science
Raef Hall |  |  |  | A current space does not exist to accommodate classrooms of this size (160+ seating)
Fine Arts Building
Stadium
Science | Modernization of existing Building #s: 10, 12, 13 | Replace buildings to include updated classrooms, area office, and faculty offices; and technology to provide modernized teaching practices and learning opportunities. | Improve student education and transfer opportunities through access to modernized equipment, as well as create a more appealing entrance to the north end of campus |  | Current Location or new location.
Fine Arts | Modernization of Building #10, Room #s, 500 - 510 | Update classrooms and spaces as well as upgrade all classroom equipment. | Improved student education and learning opportunities as well as match existing updated facility |  | Current Location.
Stadium | Modernization of Bleachers, Snack Bar, Visitor Access, Restrooms | Update stadium facilties to comply with ADA standards and improve accessibility. | Improve vistor access to bleachers, snack bars and restrooms, and increase diversity of visitors to ARC Campus |  | Current Location.
Davies Hall | Modernization of existing Building #22. | Replace highly trafficked building to provide improved learning spaces for a multitude of educational divisions | Provide easier access to classrooms with new location and improve curb appeal to the front of campus |  | West end of campus as identified in the 2012 Master Plan
Physical Education | Modernization of Locker Rooms | Update locker rooms with new flooring, showers and storage | Improve overall health and cleanliness of rooms as well as provide more storage options for students |  | Current Location.
Promenade | Create main walking Path Across Campus with access to each department along with small gathering spaces between Fine Arts and Parking Garage | Improve overrall accessibilty to classrooms and buildings for students, visitors and staff | Increase the amount of gathering space available at various locations along the route |  | From Parking Garage to Fine arts
Rose Marks Plaza | Create a "Polycultural garden" that showcases student art and sculptures | Increased gathering space to include both multicultural and horticultural aspects with updated seating, sound system | Provides a landmark to showcase our art and horticultural departments, as well as promotes cultural inclusiveness |  | Current Location.
Welcome Loop | New roadway loop in front of Welcome & Support Center | Improve new student/visitor accessibilty and parking to welcome center |  |  | NW grass area between Admin & Fine Arts
Stadium Entrance | Modernize entrance to Soccer Stadium | Improve curb appeal and increase landmarks for athletic facilities |  |  | Stadium/Parking Lot S off College Oak
Gender Neutral Facilities | Modernize spaces to include additional gender netural amenities | Update pertinent buildings with gender neutral facilities (restrooms, shower amenities, etc) to promote an inclusive environment for students, visitors and staff |  |  | One in each building
Parking Lot S | Install Solar Parking in a portion parking lot S | Increase sustainability options for the campus as well as provide shaded parking for students |  |  | Current Location
Wellness Center | Modernization of Eservices to create Wellness Center | On Campus Wellness Center to include a variety of services, specialists and assistance to our diverse population | Increase the access and promote healthcare and health assistance |  | Eservices/Student Center
Environmental Resources | Modernize facilties and classroom spaces | Update current facilties to improve safety, cleanliness and growth of student programs |  |  | Curent Location
Funeral Services | Modernization of facility and services | Campus to offer morturary parlor and full funeral services to students | Improve educational experience and learning opportunities |  | Current Location