## Sheet1
American River Campus - Master Plan Update
Potential Project Matrix
09.20.2018
| Description | Objective | Opportunities | Constraints | Desired Location
Project | General description of the project. | What campus benefit is gained through the completion of the project? | What other positive impacts are possible with the project? | What is, or would, keep the project from happening? (Other than funding.) | Where on campus should the project be located? Should it be near like uses or programs?
Technical Education/Vocation | Modernization of existing buildings and spaces. | Provide the department with modernization improvements and potentially replace the old portable buildings. | Improve the north edge of the campus and entryway from the north parking lot. |  | Current Location.
Corporation Yard | Relocation of current corporation yard uses to the south end of the campus, as identified in the 2012 Master Plan. | Create additional area on which new instructional space may be developed at the front of campus adjacent to the campus core. | Open up additional educational space within the heart of campus. Improve vehicular circulation and connectivity between parking areas along College Oak Drive. |  | South end of campus as identified in the 2012 Master Plan.
Davies Hall | Modernization of the current Davies Hall, identified as a replacement building in the 2012 Master Plan. | Replace dated classrooms and upgrade classroom technology for modern teaching practices. | Create a more appealing front door for the campus. To develop a significant open space at the south edge of the campus core, highlighting the original Ranch House on campus property. |  | Western edge of campus, as shown in the 2012 Campus Master Plan.
Administration Building | Modernization of existing administrative office and meeting spaces. | Update one of the oldest buildings on campus to provide modern office and meeting amenities and to improve the "front door" image. | Create a piece of a new student support/welcome center on campus. |  | Current Location.
Instructional Space II | New teaching space to provide for an expanded student population. | Create a new image for the science districts as well as address the formal library quad. | Improve connections between the Library area and new science courtyard/quad. |  | Dependent on the location of Science and other future buildings.
Science
Raef Hall
Fine Arts Building
Stadium
Health & Education | Rename CDC 100 & 140, and HEED 700, 701 and 702 | Help students find their classes instead of getting lost every semester |  | N/A | N/A
| More lactation rooms on campus | Help nursing mothers have a convenient and private space to pump |  | Finding rooms available to convert or make available | HEED would like on in or near the complex
| Push-button door opening for students in wheelchairs | Assist students in wheelchairs with access to classrooms |  |  | HEED classrooms
| Storage (both in classrooms and in addition to current storage space (portables or pods?) | storage for the large and overwhelming amount of supplies for CTE programs
| Flexible seating in classrooms | accommodate different teaching scenarios and student accommodations | provide more flexability for all faculty and students using the space |  | HEED classrooms (particularly 700 and 716)
| Solid overhang over the bathrooms and division office doors | keep students and faculty dry |  |  | HEED 770 and staff restrooms
| New buildings (instructional space and labs) for Allied Health Programs | current classrooms and lab space are not large enough to accommodate all allied health students | move all allied health programs into the HEED area rather than having them scattered around campus |  | In the space where the old well is, right next to the HEED complex behind the gym and/or in the place where the portable village is currently (when it is removed)
| Increase office space for HEED faculty | HEED currently has more faculty than offices Growth is expected, and we are already out of space. |  |  | Either add additional office space behind the complex (next to the tennis courts) or add a second level on the current offices.
| Create a wall or railing on the side of the parking garage facing HEED | To direct students toward walkways and avoid trampling the landscaping | Landscaping will look better, and students will not be at risk of falling in the mud when it is wet/raining |  | parking garage facing HEED