Institutional Equity Plan Meeting

9/24/18 3-5PM

Minutes

- Attendees: Tanya Anderson, Pamela Chao, Dronme, Marianne Harris,  Kate Jaques, Joshua Moon Johnson, Kelvin Burt, Judy Mays, Angela Milano, Jessica Pressley, Faryal Said, Sara Smith, Bill Lester-Zangeneh

- Check-ins: Weekend Highlights

- Discussed hopes and hope nots

  - Hopes: Learning and growth, courageous conversations, making a difference, creating friendships/bonds,  making it a reality

  - Hope Nots: Talk with no action, lack of direction, judgements, mess anything up, people avoiding meetings.

- Discussed expectations for ourselves, each other, and co-chairs

- Roles of members, chairs, governing bodies.

- Outcomes we will produce

- Discussion on Equity Plan Creation Process

  - Assemble team- Check and done

  - Retreat to set goals, roles, and foundation- Check

  - Solidify charter and process

  - Data gathering (conclude by December 15)

    - Town hall- October 26, Friday, 10AM

      - Back-up time: October 25, Thursday, 12PM

      - Location options: Gym, Black box theater 2, Library Atrium, Student Center

      - Estimated attendance: 100

      - Set-up: round tables

      - Summits

      - Announcing project

      - Campus-wide feedback

    - Stakeholder listening sessions- Assign group leads on October 1

    - Literature gathering and benchmarking

    - Campus data gathering

      - Past reports, surveys, and available information on campus climate, hiring statistic, and/or student success information.

  - Benchmarking

  - Data and information analysis (Mid-February)

    - Discussion of possibly doing an intensive retreat over two or more days for data and information analysis

  - Action creation

    - Needs identified

    - Prioritization of needs

    - Timeline of plan

    - Success measurement tools

    - Resources needed

    - Systems of accountability and institutionalized

  - Report creation

    - Draft created- March 2019

    - Feedback gathered- April

    - Edits and submission – May

  - Town Hall- Recap: March/April (second round of feedback)

- Began discussing background on project