## Sheet1
American River Campus - Master Plan Update
Potential Project Matrix
09.20.2018
| Description | Objective | Opportunities | Constraints | Desired Location
Project | General description of the project. | What campus benefit is gained through the completion of the project? | What other positive impacts are possible with the project? | What is, or would, keep the project from happening? (Other than funding.) | Where on campus should the project be located? Should it be near like uses or programs?
Technical Education/Vocation | Modernization of existing buildings and spaces. | Provide the department with modernization improvements and potentially replace the old portable buildings. | Improve the north edge of the campus and entryway from the north parking lot. |  | Current Location.
Corporation Yard | Relocation of current corporation yard uses to the south end of the campus, as identified in the 2012 Master Plan. | Create additional area on which new instructional space may be developed at the front of campus adjacent to the campus core. | Open up additional educational space within the heart of campus. Improve vehicular circulation and connectivity between parking areas along College Oak Drive. |  | South end of campus as identified in the 2012 Master Plan.
Davies Hall | Modernization of the current Davies Hall, identified as a replacement building in the 2012 Master Plan. | Replace dated classrooms and upgrade classroom technology for modern teaching practices. | Create a more appealing front door for the campus. To develop a significant open space at the south edge of the campus core, highlighting the original Ranch House on campus property. |  | Western edge of campus, as shown in the 2012 Campus Master Plan.
Administration Building | Modernization of existing administrative office and meeting spaces. | Update one of the oldest buildings on campus to provide modern office and meeting amenities and to improve the "front door" image. | Create a piece of a new student support/welcome center on campus. |  | Current Location.
Instructional Space II | New teaching space to provide for an expanded student population. | Create a new image for the science districts as well as address the formal library quad. | Improve connections between the Library area and new science courtyard/quad. |  | Dependent on the location of Science and other future buildings.
Science
Raef Hall
Fine Arts Building
Stadium
The One-Stop Center | A multi-level building that would house all student services functions (admissions and records, counseling, catagorical programs, financial aid, assessment, career, and transfer. | By housing all student services functions in one location, it creates a seamless process for students. Also it reduces confusion and students becoming discouraged and leaving the college without enrolling. | Centralizes all student services functions into one location. Reduces confusion for all (students, faculty, staff, and adminstrators). |  | Adjacent to the Student Center where the Welcome and Support Center is located currently.
Student Center- Center area | Create more defined student use space; such as modules, study pods, break out dining space. | Have more clearly defined community spaces where SS can intentionally engage students.
Storage area | Some where on campus: a place to place supplies that we only need a few times a year. | Office spaces are at a premium and some spaces that could be housing people are filled with boxes of supplies that might be only used in summer programs.
Outdoor community space | An outdoor meeting space and more outdoor community space near the student | It would provide more spaces for students to study, informal meetings to take place, and some campus events.
Food Pantry (in progress) | Space to store and distribute food as well as host educational and community building activities. | Create a one stop shop for students to pick up food, apply to Cal Fresh, Apply to medical, etc.