| Due Date | Tasks |
| --- | --- |
| Fall 2018 | DACC* meets October 5, November 2, December 7 |
| September | Data from Fiscal; work on Data Reporting Form |
| October | Oct. 15, draft to Institutional Effectiveness Council for review |
| November | Nov. 5, draft to Executive Leadership Team for review; seek input from constituency groups Nov 19, draft to Institutional Effectiveness Council for approval |
| December | Dec. 3, draft to Executive Leadership Team for approval; secure President’s approval; final drafts to DACC via email for review Dec. 7, DACC reviews reports |
| Spring 2019 | DACC meets February 1, March 1, April 5 (if needed), May 3 |
| January | By Jan. 2, final drafts to DO; send copies to Board of Trustees |
| February | Feb. 1, practice PPT report for Board of Trustees Feb. 13, presentation to Board of Trustees; document signatures by required parties |
| March | Final, signed reports to ACCJC |

DACC = District Accreditation Coordinating Committee