Equity Plan Project Team Minutes

October 22, 2018

- Present: Pam, Joshua, Cesar, Tanya, Marianne, Kelvin, Dronme, Sara, Angela, Faryal, Judy

- Town Hall

  - Facilitators and note takers assigned

    - Email on assignments and arrival time will be emailed tomorrow; arrive at 9:30AM in the Hub

  - Q&A at end of Town Hall will include President Greene

  - Cards at tables for anonymous questions

  - Two microphones for Q&A

- Continue facilitation conversations

  - Quick email follow-up for anonymous feedback through google form

    - Send on Monday 10/29

  - Discussed common barriers to facilitating dialogues on equity issues

  - Research and lit review goals

    - 1 or 2 paragraphs regarding marginalized populations/communities and then backing up with statistics (local and national)

    - We can add an appendix of a couple of paragraphs of empirical research

    - Joshua moving forward with asking about EPP programs to write mini lit review0

    - What groups do we not have an office or program supporting that we might want to do a separate lit review summary on:

      - Religious minorities (Muslim, Jewish, Sikh)

      - Women

    - Joshua will create a chart to designate who will do mini lit reviews

    - Marianne can help

    - We also need to do some lit reviews on the functional areas (HR, pro devo, mental health, etc.)

- Listening Sessions

  - Kelvin reach out for athletes to decide if we will do a listening session

  - Update date, time, and location of listening sessions by 10/24

  - Will provide pizza if needed for listening sessions ($30)