Equity Plan Project Team Notes

November 5, 2018

Agenda

- Update on “It’s Ok to be White” posters taped on campus 11/1.

  - Join discussion on Wed, 11:30AM in Community Room 2

- Town Hall

  - Review next steps

    - Bigger Space. Too close together to hear each other.

    - Technology was good for folks who were able to access not at the table.

    - Time update sooner

- Stakeholder listening sessions

  - Review list and assignments: Occur by end of fall semester.

  - Review dates, times, locations: Move forward with scheduling Latinx independently.

  - Inviting and marketing sessions: Continue to outreach to campus to invite to join stakeholders.

- Notes from Town Hall and stakeholders

  - Where to find them

    - Has been consolidated

    - Will be uploaded onto Basecamp for review by Project Team.

  - How to distribute campus-wide: IGOR

- Lit review

  - Benchmark

  - Complete by Dec 15.

  - LInk to the library reference of journals (Marianne)

  - Reference librarians (Marianne) should be able to help.

- Other campus level data to put in Basecamp for reviewing.

  - Summit focus group notes

  - PRIDE campus climate study

  - Refugee survey

  - Beaver Food Pantry survey

  - Reports from Betty G at LRCCD research.

  - Environmental scanning documents (might be useful)

  - Chancellor scorecard oriented data

  - Purchased a data on demand system (mid-spring with multiple parameter options)

  - Create a folder in basecamp for data drop off

- Overall process of analyzing findings, recommendations, and structure

  - Themes and put them on the wall and see what is the same and what is different then match them to structures.

    - What are the structures that we have in place that are creating these themes. Identifying barriers/pathways.

  - Design something differently

    - More around institutional structures, policies, training, roles and organizational structures - could move to programs offices and staffing (may not get that detailed)

- Student Equity and Achievement Plan 2019-2022

  - What this group is coming up with to align with SEA.

    - Not contradictory with one another

  - Slides in Basecamp

- Next meeting agenda 11/16

  - Continued discussion on stakeholders

  - Continued discussion on lit review and benchmarking

    - Where can Library help out

  - Update on knowledge from Facing Race Conference

  - Discussion on process moving from data analysis to recommendations