Equity Plan Project Team

Spring Timeline

Dates are hopeful dates, near, or around those dates listed

- Analyzing process

  - 1/9: Sub-team meets to discuss reviewing plan and tools

  - 1/23: Complete review

  - 1\24: Meet to discuss and create team themes of issues, needs, and areas of improvement

  - 1/29: All EP Project Team meeting to share themes from analyzing team (3+ hour meeting)

- Mapping and Action Creation

  - 2/1: Create sub-teams (e.g. Professional development programs) to focus on issues, growth opportunities for strategies and recommendations

  - 2/2-2/12: Sub-teams meet and create actions

  - 2/12: All EP Project Team meeting; Sub-teams share strategies and seek feedback (3+ hour meeting)

  - 2/22: Submit (by email) strategies and actions documents to co-chairs

    - Solutions and Action Planning

      - Current level (“We are already making efforts and let’s keep this up”)

      - Enhancements (“We have some efforts, but we need to do more or different”)

      - Restructuring (“We need a change our structure, system, process, or organization”)

      - Creation (“We have nothing now and need to create something”)

  - 2/27: Review compiled action document (very rough draft of report)

  - 2/27-3/4: Pam, Joshua, and Cesar write draft 1

  - 3/4: Round 2 review and discuss report

  - 3/14: Round 3 review and discuss report

  - 3/18: Submit official draft to IEC

  - TBD: Receive feedback

  - 3/27: Meet to discuss feedback and revise

  - 4/1: Submit to ELT

  - 4/8: Submit Draft 2 to IEC