## Sheet1
Disproportionate Impact |  |  | Educational Master Plan |  |  | Professional Development and Training |  |  | Strategic Enrollment Management |  |  | Sustainability Improvement
Sponsoring Council: Student Success Council |  |  | Sponsoring Council: Student Success Council |  |  | Sponsoring Council: Institutional Effectiveness Council |  |  | Sponsoring Council: Student Success Council |  |  | Sponsoring Council: Operations Council
Meeting Date | Council | Desired Outcome | Meeting Date | Council/Constituency Group | Desired Outcome | Meeting Date | Council | Desired Outcome | Meeting Date | Council | Desired Outcome | Meeting Date | Council | Desired Outcome
11/26/2019 (11/19/2019 is 3rd Tuesday) | Student Success Council (progress report) | x 1st Reading | draft - mid-to-late October | President’s Executive Staff and | Informal feedback on the working draft | March 16, 2020* | Institutional Effectiveness Council | x 1st Reading | 2020-01-23 | Academic Senate | x 1st Reading | February 25, 2020* | Operations Council | x 1st Reading
|  | o 2nd Reading |  | Academic Senate Leadership |  |  |  | o 2nd Reading |  |  | o 2nd Reading |  |  | o 2nd Reading
2020-03-03 | Student Success Council (final report) | x 1st Reading |  |  |  | April 6, 2020* | Executive Leadership Team | x 1st Reading | February 4, 2020* | Student Success Council | x 1st Reading | March 24, 2020* | Operations Council | o 1st Reading
|  | o 2nd Reading | November 14, 2019* | Academic Senate | x 1st Reading |  |  | o 2nd Reading |  |  | o 2nd Reading |  |  | x 2nd Reading - Recommendation to ELT
2020-03-17 | Student Success Council | o 1st Reading |  |  | o 2nd Reading | April 20, 2020* | Institutional Effectiveness Council | o 1st Reading | 2020-02-13 | Academic Senate | o 1st Reading | April 6, 2020* | Executive Leadership Team | x1st Reading
|  | x 2nd Reading | November 6-14, 2019 – See groups | Review by other constituency groups: | Any suggested changes provided to project lead/co-lead |  |  | x 2nd Reading - Recommendation to the ELT |  |  | x 2nd Reading |  |  | o 2nd Reading
2020-03-12 | Academic Senate | x 1st Reading |  | - Associated Student Body (11/7 or 11/14*) |  | May 4, 2020* | Executive Leadership Team | o 1st Reading | February 18, 2020* | Student Success Council | o 1st Reading | May 4, 2020* | Executive Leadership Team | o 1st Reading
|  | o 2nd Reading |  | - Classified Senate (11/13*) |  |  |  | x 2nd Reading |  |  | x 2nd Reading - Recommendation to the ELT |  |  | x 2nd Reading
2020-03-26 | Academic Senate | o 1st Reading |  | - Management Team (11/6*) |  |  | Note: Deliverable #2 is a section within a comprehensive Employee Development and Retention Plan. If preferred, this deliverable could be held for future review of the entire plan by the ELT rather than considering individual sections. If this occurs, the short-term priorities could be submitted earlier for governance review which would adjust the dates above. |  | March 2, 2020* | Executive Leadership Team | x 1st Reading
|  | x 2nd Reading - Recommendation to the ELT | November 19, 2019* | Student Success Council | x 1st Reading | [5 empty] | o 2nd Reading
2020-04-06 | Executive Leadership Team | x 1st Reading |  |  | o 2nd Reading |  |  |  | April 6, 2020* | Executive Leadership Team | o 1st Reading
|  | o 2nd Reading | November 28, 2019* is Thanksgiving meeting will be 11/21/19 | Academic Senate | o 1st Reading | [5 empty] | x 2nd Reading
2020-05-04 | Executive Leadership Team | o 1st Reading |  |  | x 2nd Reading - Recommendation to the SSC
|  | x 2nd Reading | December 2, 2019* | Executive Leadership Team | x 1st Reading
o 2nd Reading
|  |  | December 3, 2019* | Student Success Council | o 1st Reading
|  |  |  | Council | x 2nd Reading – Recommendation to the ELT
|  |  | February 3, 2020* | Executive Leadership Team | o 1st Reading
x 2nd Reading