ISER Project Team Timeline

Spring 2020

- Project team initiated by Executive Leadership Team (December 2019)

- Establish project team charter (February 2020)

- Identify project team members including standard leads (February 2020)

- ACCJC training held at DO on March 17 from 8:30am-12:30pm

  - all DACC members as well as standards leads must attend (others are welcome as space permits)

- ACCJC liaison visits college for meet and greet

  - March 18, 9:00-11:00 am at ARC

- Project team develops ISER outline (April)

- Potential Quality Focused Essay (QFE) topics are determined (April-May)

Fall 2020

- Organize accreditation information campaign

- Develop document library, track information, and organize evidence

- Provide updates for the college community (flex, senates, etc.)

- Conduct accreditation surveys

- Writing: Analysis and Evaluation

- Writing: Conclusion

- Writing: Improvement Plans

- Share information with DACC monthly

- Incorporate District information shared for consistency

Spring 2021

- Monitor information campaign

- Develop document library, track information, and organize evidence

- Hold meetings and provide updates for College Community (flex, senates, etc.)

- Complete evidence list

- Seek feedback from college constituencies and faculty/staff/students on programs and services of the College

- College accreditation workgroup integrates feedback and completes revisions

- Share information with DACC monthly

- Full draft of ISER and QFE completed