| Part I: Introduction and Conceptual Framework (2 weeks) |  |  |
| --- | --- | --- |
| Wednesday 10/14/20 | Meeting 1: - Review DI Report Structure (20 mins) - Timeline - Profile of API students at (50 mins) - Demographics and disproportionate impact - Recent efforts or programs that influence the current student experience (e.g., PRISE) - Conceptual Framework (30 mins) - Critical Race Theory - Validation Theory - Others? - Break (10 min) - Wrap-up and next steps (10 mins) | Team Homework due by Meeting 2: - Review and decide preferred conceptual framework. - Submit any resources to Raquel & Neue for API History summary. |
| Wednesday 10/21/20 | Meeting 2: - Review and discuss - Conceptual Framework (15 mins) - API History draft (45 mins) (CO 1)* *CO = Charter Objective - Break (10 mins) - Review and discuss Profile of API students (45 mins) (CO 2) - Wrap-up and next steps (5 mins) | Team Homework due by Meeting 3: - Submit suggested edits to Conceptual Framework and API History sections. |
| Part II: Literature Review and Data Collection (2 weeks) |  |  |
| Wednesday 10/28/20 | Meeting 3: - Identify institutional barriers (70 mins) - Break (10 mins) - Literature Review planning (30 mins) - Identify streams - Assignments? - Wrap-up and next steps (10 mins) | Team Homework due by Meeting 4: - Writing assignments (if applicable), e.g. prepare a synopsis of assigned article. |
| Wednesday 11/4/20 | Meeting 4: - Share-out/discussion of Literature Review (60 mins) - Break (10 mins) - Review and discuss Profile and Institutional Barriers draft (30 mins) (CO 3) - Assess need for focus group/additional literature (15 mins) - Wrap-up and next steps (5 mins) | Team Homework due by Meeting 5: - Read and provide comments on Profile and Institutional Barriers draft. |
| Wednesday 11/11/20 | Veteran’s Holiday - No Meeting |  |
| Part III: Findings and Analysis (3 weeks) |  |  |
| Wednesday 11/18/20 | Meeting 5: - Review and discuss Literature Review draft (20 mins) (CO 4) - Review and discuss Survey results and findings (45 mins) - Break (10 mins) - Survey discussion continued; plan 2nd round literature review? (40 mins) - Wrap-up and next steps (5 mins) | Team Homework due by Meeting 6: - Writing assignments (if applicable), e.g. prepare a synopsis of assigned article. |
| Monday 11/23/20 (?) Thanksgiving week | Meeting 6: - Synthesis of lit review and data findings; discussion of high impact social justice practices, services, and teaching methods (75 mins) (CO 5) - Break (10 mins) - Discuss Framework for Recommendations (30 mins) - Wrap-up and next steps (5mins) | Team Homework due by Meeting 7: None |
| Part IV: Conclusions and Recommendations (3 weeks) |  |  |
| Wednesday 12/2/20 | Meeting 7: - Share-out/discussion of 2nd round lit review and any new data (30 mins) - Discuss conclusions and recommendations (45 mins) - Break (10 mins) - Conclusion and recommendation discussion continued (30 mins) - Wrap-up and next steps (5 mins) | Team Homework due by Meeting 8: TBD |
| Wednesday 12/9/20 | Meeting 8: - Review and discuss Framework and Recommendations draft (60 mins) (CO 6) - Break (10 mins) - Recommendations draft discussion continued (30 mins) - Wrap-up and next steps (15 mins) | Team Homework due by Meeting 9: - Read and provide comments on Framework and Recommendations draft. |
| Wednesday 12/16/20 | Meeting 9: - Review and discuss first full draft (75 mins) | Team Homework due by Meeting 10: None. |
| Part V: Draft Review and Completion (2-3 weeks) |  |  |
| Wednesday 1/13/20 (?) | Meeting 10: - Review and discuss first full draft; mark-up for suggested edits (90 mins) | Team Homework due by Meeting 11: - Submit suggested edits to draft |
| Wednesday 1/27/20 | Meeting 11: - Review and approve draft for Student Success Council First Read (45 mins) - Wrap-up and next steps (15 mins) | Team Homework due by Meeting 12: TBD |
| TBD | Meeting 12 and beyond As needed; may drop down to one meeting per month from February through April, to go over college input and revisions. |  |