| # | Project | Summary | Status as of Fall 2020 |
| --- | --- | --- | --- |
| 1 | Areas of Interest | Implemented in 2018-19 and published on website: https://arc.losrios.edu/academics/areas-of-interest | At Scale |
| 2 | Program Roadmaps | “Top 10” completed in 2018-19; Remainder posted in 2020: https://arc.losrios.edu/academics/arc-program-road-maps | At Scale |
| 3 | Program Paths Management | Committee created in 2018-2019; Program map management tool determined in 2019-20 and implementation is in progress | Scaling in Progress |
| 4 | Pathways to ARC (focused outreach/recruitment) | To be implemented in Fall 2021 | Planning to Scale |
| 5 | Simplify the Front Door (prospective student experience) | Scaling in progress as of Spring 2020 | Scaling in Progress |
| 6 | Achieve at ARC Scaling (new student onboarding) | Planning to Scale: Spring 2020 through Fall 2022 | Planning to Scale |
| 7 | First Term Schedule Options (initial courses for the path) | Phase I developed and planning to implement for Fall 2021; Phase II to be implemented for Fall 2023 | Planning to Scale |
| 8 | Pathway Communities (connection to area of interest) | Virtual HomeBase Pathway Communities implemented in Fall 2020; Physical and virtual implementation in Fall 2021 in ideal conditions https://inside.arc.losrios.edu/inside-arc-news/homebase-pathway-communities | Planning to Scale |
| 9 | Peer Mentoring | Scheduled implementation in Spring 2021 | Planning to Scale |
| 10 | Physical Access and Navigation (Wayfinding) | Implemented in 2019 https://wayfind.arc.losrios.edu/ | Scaling in Progress |
| 11 | Physical Access and Navigation (One-Stop Welcome Center) | Implemented in Fall 2019 | At Scale |
| 12 | First Term Experience (FYE Course) | Planned implementation in Fall 2022 | Planning to Scale |
| 13 | Alternate Experience(s) for the “Not New” Student | Planning to implement Fall 2021-Spring 2022 | Not Occurring |
| 14 | Transition Services (Career and Transfer) | Implementation planned Fall 2021 | Not Systematic |
| 15 | Evaluation Plan | Implementation planned Spring 2021-Spring 2022 | Not Occurring |
| 16 | Intersection with Districtwide Processes (Hobsons, etc.) | TBD Districtwide implementation | Not Occurring |
| 17 | Supporting Technologies (G.E. Search Tool) | Planned for Fall 2019-Spring 2020 | Not Occurring |
| 18 | Supporting Technologies (Student Communications Platform) | Starfish implemented in Fall 2020 | Planning to Scale |
| 19 | Supporting Technologies (Alert and Progress Reporting) | Starfish implemented in Fall 2020 | Planning to Scale |
| 20 | Pre-Implementation Work | Business process analysis conducted Fall 2018; implementation in progress | Planning to Scale |
| 21 | Governance Redesign | Implemented at scale in 2019 https://inside.arc.losrios.edu/governance | At Scale |
| 22 | Recommendations: ARC Online 2.0 | Implementation to begin Spring 2021 | Planning to Scale |
| 23 | Recommendations: ELSS (Ad Astra) | No formal recommendations. Determined in Spring 2019 to be referred to Districtwide process for implementation | Not Occurring |
| 24 | Recommendations: Facilities Master Plan | Timeline for implementation of major facilities projects TBD | Planning to Scale |
| 25 | Recommendations: Institutional Equity Plan | The Office of Equity and Inclusion and Interim Dean of Equity and Inclusion were created and funded in Fall 2019 as a result of this plan. Duties include Compliance (Title IX, Title V, Equity Officer, Grievance) and campuswide capacity building (Professional Development and Executive-level consultation). Additional implementation planned through 2020-21 | Planning to Scale |
| 26 | Recommendations: Integrated Planning Improvement | Integrated Planning Guide, Portal, and new planning process implemented in 2018-2019 | At Scale |
| 27 | Recommendations: Wellness Center | Wellness Center facility implemented in Fall 2019. Additional programming and services implemented in Spring 2020 | Planning to Scale |
| 28 | Recommendations: Clarify Program Paths (2018-19) | This project was re-chartered for a second year (2018-2019). Implementation of recommendations from this report TBD per collaboration with Districtwide processes | Scaling in Progress |
| 29 | Recommendations: Disproportionate Impact (African American, Latinx, Native American) | Introduced findings at Fall 2020 Convocation. Created positions (bi-lingual support specialists, Black Student Success Coordinator, Men of Color Success Initiatives, Professional Development Liaisons). Created Black Student Success Center. Developed relationships with Men of Color Success Initiatives (Improve Your Tomorrow, A2MEND, etc.). Implementation of DI recommendations planned for Fall 2020-Fall 2021. | Planning to Scale |
| 30 | Recommendations: Education Master Plan | Implementation of guiding imperatives planned through Fall 2031 | Planning to Scale |
| 31 | Recommendations: Professional Development and Training | Fall 2020 implementation: CTL has been moved under Office of Equity and Inclusion with a specific focus on Equity-minded professional development for all development opportunities. Further PD implementation planned for Spring-Fall 2021 | Planning to Scale |
| 32 | Recommendations: Strategic Enrollment Management | Strategic Enrollment Management team recommendations implemented Fall 2020. Additional recommendations planned for Spring 2021 implementation | Planning to Scale |
| 33 | Recommendations: Sustainability Improvement | Implementation began in Summer 2020 with renaming of Campus Operations to include Sustainability. Further implementation ongoing through Fall 2020 and to be continued through Spring 2021 | Scaling in Progress |
| 34 | Accreditation Self-Evaluation | Project team chartered by Executive Leadership Team began work in Fall 2020 | TBD |
| 35 | Disproportionate Impact: Asian-Pacific Islander, LGBTQI+ | Project team chartered by Student Success Council began work in Fall 2020 | TBD |
| 36 | Disproportionate Impact: LGBTQI+ | Project team chartered by Student Success Council began work in Fall 2020 | TBD |
| 37 | Technology Master Plan | TBD | TBD |

Status Key

| Status (Scale of Adoption) | Definition |
| --- | --- |
| Not occurring | College is currently not following, or planning to follow, this practice |
| Not systematic | Practice is incomplete, inconsistent, informal, and/or optional |
| Planning to scale | College is/has made plans to implement the practice at scale and has started to put these plans into place |
| Scaling in progress | Implementation of the practice is in progress for all students |
| At scale | Practice is implemented at scale – that is, for all students in all programs of study |

1. AREAS OF INTEREST

Areas of interest are designed to assist students in exploring potential majors and career options.  They also serve as an organizing framework for program roadmaps and pathway communities.

Existing Areas of Interest

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Submit web site content for areas of interest | End of Spring 2019 | Clarify Program Paths project leads | n/a | At scale | [Clarify Program Paths Rec. #1] |
| 1.2 | Post areas of interest and related content on the new college web site with appropriate organization for easy navigation | Summer 2019 | Public Information Officer or designee | n/a | At Scale | [Clarify Program Paths Rec. #1] |
| 1.3 | Publicize areas of interest to employees to inform of availability, train on intended use, and next steps | Fall 2019 | Public Information Officer | n/a | Scaling in progress | Timing impacted by changes to areas |
| 1.4 | Develop any new marketing/outreach materials that are needed to highlight areas of interest (needed before February 2019 for outreach purposes) | Fall 2019 | Public Information Officer | n/a | Scaling in progress | Timing impacted by changes to areas |
| 1.5 | Update existing publications, forms, and materials such as the college catalog | On regular cycle | Public Information Officer (or person responsible for specific publication/form) | n/a | Scaling in progress | Timing impacted by changes to areas |

Cross-References: #6 – Achieve at ARC Scaling; #8 - Pathway Communities

2. PROGRAM ROADMAPS

Program roadmaps are a suggested sequence of courses that would permit students to progress through a program in a timely manner.  They are not intended to be an individual student’s educational plan, but rather a general navigational tool for anyone considering the program. Two roadmaps will be created per program (full-time and part-time version).

Existing Program Roadmaps

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Confirm top 10 programs in each area of interest | Early Fall 2018 | Clarify Program Paths project leads | n/a | At Scale | [Clarify Program Paths Rec. #2] |
| 2.2 | Develop initial program roadmaps for the top 10 programs in each area of interest (90 programs total; two versions per program – FT/PT) | By April 2019 | Clarify Program Paths project leads | n/a | At Scale | [Clarify Program Paths (2018-19) Appendix B] |
| 2.3 | Submit web site content for top 10 program roadmaps in each area of interest | Upon adoption (est. May 2019) | Clarify Program Paths project leads | n/a | At Scale | [Clarify Program Paths Rec. #2] |
| 2.4 | Post roadmaps on the new college web site with appropriate organization for easy navigation | Summer 2019 | Public Information Officer or designee | n/a | At scale | [Clarify Program Paths Rec. #2] |
| 2.5 | Publicize initial program roadmaps to employees to inform of availability, intended use, and next steps | Early Fall 2019 | Clarify Program Paths project leads | n/a | At scale | Additional publicity will take place when move away from PDF maps occurs |
| 2.6 | Continue building out initial program roadmaps for the remaining programs (approx. 210 programs; two versions per program – FT/PT) | By Spring 2020 | Clarify Program Paths project leads | n/a | Planning to Scale | [Clarify Program Paths Rec. #2] |
| 2.7 | Submit web site content for remaining program roadmaps in each area of interest | Upon adoption | Clarify Program Paths project leads | n/a | Planning to Scale | [Clarify Program Paths Rec. #2] |
| 2.8 | Post remaining roadmaps on the new college web site with appropriate organization for easy navigation | By Summer 2020 | Public Information Officer or designee | n/a | Planning to Scale | [Clarify Program Paths Rec. #2] |

Cross-References: #1 - Areas of Interest

3. PROGRAM PATHS MANAGEMENT

An entity needs to be designated to assume responsibility for ongoing maintenance and assessment of areas of interest and program roadmaps.  This responsibility would include updating roadmaps to reflect changes in curriculum and scheduling, managing planned rotation of default general education courses, and other related tasks.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Propose committee to maintain areas of interest and program roadmaps | Mid-Fall 2018 | Clarify Program Paths project leads | n/a | At Scale | [Clarify Program Paths Rec. #3] |
| 3.2 | Develop requirements for technology to support ongoing maintenance of roadmaps | Mid-Fall 2018 | Clarify Program Paths project leads; Dean, Planning, Research and Technology | n/a | Scaling in Progress | [Clarify Program Paths Rec. #3] |
| 3.3 | Propose technology to support program roadmap creation, publication, and management | Mid-Fall 2018 | Clarify Program Paths project leads; Dean, Planning, Research and Technology | n/a | At Scale | [Clarify Program Paths Rec. #3] |
| 3.4 | Establish committee (pending approval of proposal) | Late Fall 2018 | Academic Senate | n/a | At Scale | [Clarify Program Paths Rec. #3] |
| 3.5 | Establish committee practices and structures | Spring 2019 | Program Pathways Committee | n/a | At Scale | [Clarify Program Paths Rec. #3] |
| 3.6 | Acquire/develop and implement technology to support program roadmap creation, publication, and management | Spring and Summer 2019* | Program Pathways Committee with IT/programming support | n/a | Scaling in Progress | *Tentative timeline as software specifications are unknown |
| 3.7 | Develop process for incorporating new programs | Spring 2019 | Program Pathways Committee | n/a | Scaling in Progress |  |
| 3.8 | Develop cycle and process for modifying areas of interest and program roadmaps | Spring 2019 | Program Pathways Committee | n/a | Scaling in Progress |  |
| 3.9 | Document all of the related systems, publications, and other areas that must be updated after each modification | Spring 2019 | Program Pathways Committee | n/a | Scaling in Progress | Consider public-facing content (e.g., web site), student-facing systems, employee-facing systems, and various publications |
| 3.10 | Communicate processes to the campus | Early Fall 2019 | Program Pathways Committee | n/a | Scaling in Progress |  |

Cross-References: #2 – Program Roadmaps

4. PATHWAYS TO ARC (Outreach & Recruitment)

The Educational Pathways Action Plan was previously developed to focus outreach and recruitment efforts around ARC’s four feeder high schools along with key community outreach strategies. The plan aligns with the direction of the ARC Redesign, but has not yet been implemented.  One particular goal of this component is to engage 6-12th grade students in clear, well-coordinated pathways leading from secondary education to the front door of American River College.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Review, and update if appropriate, the previously developed Educational Pathways Action Plan; sunset the plan | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic | Educational Pathways Action Plan created by the Pathways Task Force in early 2015 |
| 4.2 | Identify any resource needs that are essential to successful implementation of the plan which includes opt out scheduling for full-time, first-time recent high school graduates | Spring 2021 | AVP, Student Services, VPI, VPSS | n/a | Not Systematic | See Section on First Term Schedule Options |
| 4.3 | Implement the planned migration from the existing outreach/recruitment practices to the new Pathways to ARC model | Beginning Spring 2021 for Fall 2021 cohort | Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic |  |
| 4.4 | Assess effectiveness of the pathways and related outreach/recruitment strategies | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities; Institutional Research Office | n/a | Not Occurring |  |

Cross-References: Referred to Other Processes

5. SIMPLIFY THE FRONT DOOR (Prospective Student Experience)

The front door of ARC must provide an inviting, easy-to-access entry point for prospective students that streamlines and cohesively connects communication and activities from the first point of contact to the new student’s engagement with a pre-designed onboarding process such as Achieve at ARC.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Assess the employee experience using existing business processes to serve and interact with prospective students | Spring 2019/Fall 2019/Spring 2020 | PES; VPSS Office, District Front Door Design Team | n/a | Not Systematic |  |
| 5.2 | Conduct one or more focus groups with Achieve at ARC participants or other recent applicants to glean further insight into the front door experience | Spring 2019 | Dean, Admissions and Transition Services; Institutional Research Office | n/a | Scaling in Progress | Ongoing |
| 5.3 | Assess the prospective student experience from at least three viewpoints: - Inquiries – prospect initiates contact with college - Outreach – college initiates contact with prospect - Stealth applicants – no contact with college prior to application | Fall 2019/Spring 2020 | Dean, Admissions and Transition Services; Dean, Equity Programs and Pathways | n/a | Not Occurring | Districtwide process |
| 5.4 | Explore technologies and integration of technology to support student communication at the front door. | TBD – see note | VPSS Office; Communications, District Front Door Design Team | n/a | Not Systematic | Involves multiple groups including IEPI/PRT process; Technology workgroup; districtwide Simplify the Front Door group; Hobsons and HighPoint implementation teams |
| 5.5 | Rename/brand Steps to Success for ARC model | Fall 2019/Spring 2020 | VPSS Office, District Front Door Design Team | n/a | Scaling in Progress | Districtwide process. |
| 5.6 | Identify and prioritize desired changes based on assessment and focus group input | Spring 2020 | PES; VPSS Office | n/a | Not Systematic | Districtwide process |
| 5.7 | Plan and implement the desired changes | Fall 2020 | VPSS Office | n/a | Not Systematic | Districtwide process |

Cross-References: #6 – Achieve at ARC Scaling; #16 – Intersection with Districtwide Processes; #18 – Student Communication Platform; see also outreach-related and communication-related items under Referred to Other Processes

6. ACHIEVE AT ARC SCALING

Achieve at ARC was launched in early Spring 2018 to provide a more cohesive onboarding experience to incoming students.  During summer 2018, it is expected to serve approximately 1000 students.  Scaling would enable the full new student population (approximately 3500 new students each fall plus additional students for other terms) to be served.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Develop full plan for scaling Achieve at ARC including connections to success teams, areas of interest, and other recommended features of the new student experience | By Spring 2019 | Dean, Student Services -Counseling, and Transfer Services | n/a | At Scale |  |
| 6.2 | Develop needs assessment tool and processes | By Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Planning to Scale |  |
| 6.3 | Identify scalable career assessment and exploration tools and processes to support student early selection of programs of study | Fall 2022 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services -Counseling and Transfer Services; Dean, Student Services - Student Support Services; | n/a | Planning to Scale | [Start Right, V.B] ARC has subscribed to Focus2Career assessment to help achieve this goal. |
| 6.4 | Ensure financial aid assistance and financial literacy is incorporated in scaled model | Spring 2021 | AVP, Student Services; Dean, Student Services – Counseling and Transfer Services; Interim Dean, Outreach, FYE, and Pathway Communities; Dean of Student Support Services | n/a | Planning to Scale | [Start Right, V.F] |
| 6.5 | Develop process for student to explore, select, and change programs of study, and use data to inform pathway communication and activities for students | By Spring 2020 | Dean, Admissions and Transition Services; Dean, Student Services -Counseling, and Transfer Services; Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic | [Start Right, XIII.B] |
| 6.6 | Work with success teams, once established, to ensure case management function is seamless from onboarding through the first term and beyond | By Spring 2022 | Dean, Student Services -Counseling, and Transfer Services; Interim Dean, Outreach, FYE, and Pathway Communities; Dean of Student Support Services | n/a | Scaling in Progress |  |
| 6.7 | Achieve@ARC case management implemented at full scale for all new students. | Spring 2020 (for Fall 2020 students) | Dean, Student Services -Counseling, and Transfer Services; Interim Dean, Outreach, FYE, and Pathway Communities | n/a | At Scale |  |
| 6.8 | Leverage functionality of Hobsons/HighPoint once available | TBD – Districtwide | VPSS Office | n/a | Not Occurring (Spring 2020) |  |

Cross-References: Intersection with Districtwide Processes

7. FIRST TERM SCHEDULE OPTIONS

Schedule options would allow new students to enroll in a packaged first term schedule (either full-time or part-time version) prior to full educational planning.  The student could modify course choices as desired. Opportunities would need to be provided for the student to receive guidance if the packaged schedule does not meet individual student needs.

Phase I (before roadmaps):  Basic schedule with math, English, and introductory general education course(s)

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Define parameters for creating first term schedule options - student population which would be offered packaged schedules (e.g., new students with no prior units who are seeking a degree or transfer) - excluded program maps for alignment purposes (e.g., certificate programs) - full-time/part-time unit range - desired number of packaged schedules (e.g., one FT/PT per area of interest + undecided option) | Fall 2020 | Dean, Student Services - Counseling, and Transfer Services; VPI Office; Interim Dean, Outreach, FYE, and Pathway Communitie; AVPs of Instruction | n/a | Planning to Scale | [Start Right V.A] |
| 7.2 | Develop enrollment forecasting model for packaged courses (and ideally sections) that considers historical trends, enrollment patterns, likely variations due to adoption of areas of interest/program roadmaps, multiple points of entry during the term, guaranteed courses, which students will use packaged schedules, etc. | By Spring 2021 | VPI, AVPs, all deans, VPSS | n/a | Planning to Scale | While the ELSS is a possibility, it may not be able to handle this type of projection due to lack of data about certain criteria and assumptions unique to the redesign |
| 7.3 | Work with Outreach and Achieve at ARC to plan/map delivery method(s), timing, and technology to provide students with the first term schedule options | By Spring 2021 | Deans of Student Services, VPSS, Outreach, and Achieve Center | n/a | Planning to Scale |  |
| 7.4 | Develop Phase I packaged first term schedules based on previously defined parameters | By Summer 2021 | VPI, VPSS, AVPs, Deans | n/a | Planning to Scale | Include math, English, and general education course(s) |
| 7.5 | Run enrollment demand projections for packaged courses that consider both historical trends, likely variations due to adoption of areas of interest/program roadmaps, and multiple points of entry during the term | Late Summer/Early Fall 2021 | VPSS, VPI, Research, Dean of Admissions, AVPs | n/a | Planning to Scale |  |
| 7.6 | Commit to scheduling practices with sufficient FTE to guarantee available sections to meet projected demand of students using Phase I packaged schedules | Fall 2021 | VPI, AVPs, Deans of Instruction | n/a | Planning to Scale | [Start Right V.A.1.d) |
| 7.7 | Launch to incoming students via Achieve at ARC | Spring 2021 (for Fall 2021) | VPSS, Deans of Student Services, Outreach | n/a | Planning to Scale |  |
| 7.8 | Capture feedback to assess unanticipated barriers and/or need for refinement - Feedback from students during pre-term experience - Feedback from counselors/enrollment services - Feedback from schedulers/instructional administrators/instructional faculty | Spring 2022 | Research | n/a | Not Occurring |  |

Phase II (after roadmaps): Determine packaged courses based on the full set of program roadmaps

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 7.9 | Consider feedback from Phase I and determine any desired modifications | Spring 2022 | VPI, VPSS, AVPs, Deans | n/a | Not Occurring |  |
| 7.10 | Refine the enrollment projection model to incorporate any relevant modifications | By Spring 2023 | VPI, VPSS, AVPs | n/a | Not Occurring |  |
| 7.11 | Develop Phase II packaged first term schedules based on previously defined parameters and aligned with program roadmaps as appropriate | By Spring 2023 | VPI, AVPs, VPSS, Deans, Clarify Program Paths | n/a | Not Occurring | [Start Right, V.A] The full set of roadmaps are expected by Spring 2020. |
| 7.12 | Run enrollment demand projections for expected courses that consider both historical trends, likely variations due to adoption of areas of interest/program roadmaps, and multiple points of entry during the term | Late Summer/Early Fall 2022 | Research | n/a | Not Occurring |  |
| 7.13 | Commit to scheduling practices with sufficient FTE to guarantee available sections to meet projected demand of students using Phase II packaged first term schedules | Fall 2022 | VPI, AVPs, Deans of Instruction | n/a | Not Occurring | [Start Right V.A.1.d) |
| 7.14 | Launch to incoming students via Achieve at ARC | Spring 2023 (for Fall 2023) | VPSS, Deans of Student Services, Outreach | n/a | Not Occurring |  |
| 7.15 | Capture feedback to assess unanticipated barriers and/or need for refinement | Summer 2023 | Research | n/a | Not Occurring |  |
| 7.16 | Refine packaged schedules as needed based on feedback | Fall 2023 | VPS, VPSS, AVPs, Deans, Research | n/a | Not Occurring |  |

Cross-References: #2 – Program Roadmaps; #6 – Achieve at ARC Scaling; #23 – ELSS; Related Project Work

8. PATHWAY COMMUNITIES (Ongoing Connection)

Pathway communities would be structured around areas of interest and provide an ongoing connection from first term throughout the student’s program.  They focus on academic, program- and career-specific information as well as events and communications relevant to all students in the area of interest.   Within Pathway Communities, Success Teams would provide initial and ongoing support including case management and wrap-around services.  Success teams would be the vehicle for the case management function as students transition from Achieve at ARC to aligned Pathway Communities.  The pre-term experience is an extended orientation that would take place over multiple days.  It is likely to involve areas of interest, opportunity to modify packaged courses in first term schedule options, success teams, and pathway communities.  The existing GPS structure needs to be assessed for potential restructuring or consolidation with the scaled Achieve at ARC and pre-term experience to avoid unnecessary duplication.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Develop the use of pathway communities as the primary vehicle for providing academic, program- and career-specific information to current students | Fall 2019 | VPI Office; VPSS; Interim Dean, Outreach, FYE, and Pathway Communities | n/a | At Scale | [IPaSS VIII] |
| 8.2 | Develop and adopt the standard practices for activities and/or outcomes required of all pathway communities | Fall 2019 | PES | n/a | At Scale | These are the minimum thresholds expected of any pathway community |
| 8.3 | Revisit areas of interest from an operational perspective to determine whether adjustments or consolidation are needed for better facilitation of the student experience | Fall 2020 | PES | n/a | Scaling in Progress |  |
| 8.4 | Determine the mechanism for attaching a student to a pathway community once an area of interest is declared | By Fall 2020 | VPI Office; Interim Dean, Outreach, FYE, and Pathway Communities, VPSS, PES | n/a | At Scale | Data may come from the process for selecting an area of interest contained in the Achieve at ARC scaling timeline |
|  | Success Teams (1st Term & Ongoing Support) |  |  |  |  |  |
| 8.5 | Clarify roles of the primary administrator and Student Success Council related to success teams | Fall 2019 | President’s Executive Staff, SSC Chairs | n/a | Scaling in Progress | [Start Right III.B – referred to as gateways] |
| 8.6 | Develop and adopt criteria that defines the attributes required of all success teams | Fall 2018 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | At Scale | [Start Right III.A]; these are “must have” components to be considered a success team |
| 8.7 | Implement tools needed to assign students to success teams and to monitor services provided. | Fall 2020 | Interim Dean, Outreach, FYE, and Pathway Communities, AVP, VPSS, AVPI | n/a | Planning to Scale | Starfish was implemented in Fall 2020 |
| 8.8 | Develop and implement a case management model and identify appropriate staffing. | Fall 2018 | Dean, Student Services -Counseling, and Transfer Services | n/a | At Scale |  |
| 8.9 | Provide continued training to success team members to support student success outcomes | Fall 2018 and ongoing | President’s Executive Staff or designee | n/a | Scaling in Progress |  |
| 8.10 | Develop and implement standard practices for activities and/or objectives required of all success teams | By Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, PES | n/a | Planning to Scale | These are minimum thresholds expected of any success team |
| 8.11 | Establish the process for creating new success teams with an intentional focus (e.g., mandated groups) | By Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Planning to Scale | [Start Right XII.C-XII.N] |
| 8.12 | Evaluate existing entities and determine the needed resources to bring student success teams to scale | Summer 2021 | VPSS Office | n/a | Scaling in Progress |  |
| 8.1 | Determine how existing learning communities could be incorporated into the framework of a success team as a complementary support | By Summer 2021 | VPSS, VPI | n/a | Planning to Scale |  |
| 8.14 | Determine process by which students connect to a success team and who may be served by another program to streamline services and support. | By Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services, Counseling, and Transfer Services, VPSS | n/a | Planning to Scale |  |
| 8.15 | Allocate resources to allow setup and launch of any new success teams before summer 2020 | By Spring 2021 | President’s Executive Staff of designee, VPSS Office | n/a | Scaling in Progress |  |
| 8.16 | Fully scaled success team model becomes operational in conjunction with the pre-term experience | Summer 2021 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services - Counseling, and Transfer Services; Dean, Student Services – Student Support Services, VPSS | n/a | Planning to Scale |  |
| 8.17 | Pre-Term Experience (Extended Orientation) |  |  |  |  |  |
| 8.18 | Assess and utilize what was learned from the Summer 2018 extended orientation to fully design a pre-term experience and potentially an alternative experience for late-start students | Fall 2018 | Dean, Equity Programs and Pathways, VPSS | n/a | Scaling in Progress | [Start Right XI] |
| 8.19 | Coordinate with Achieve at ARC, Success Teams, Pathway Communities, Financial Aid, CDC, and others as needed to refine the design | Early Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Planning to Scale |  |
| 8.20 | Determine a process for students to identify their programs of study and first semester course options. | Spring 2021 for Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS; VPI | n/a | Not Systematic |  |
| 8.21 | Schedule experiences for the Fall 2020 semester (pre-term events beginning in summer) | Fall 2019 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Planning to Scale |  |
| 8.22 | Advertise pre-term experience opportunities to students | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Planning to Scale |  |
| 8.23 | Conduct first set of experiences and collect feedback from those involved | Summer 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, Research | n/a | Planning to Scale |  |
| 8.24 | Refine experience as needed | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Planning to Scale |  |
|  | Get Connected (formerly GPS) |  |  |  |  |  |
| 8.25 | Assess the existing GPS structure considering the plan for the overall redesigned experience (Note: GPS sessions concluded in July and in August 2018. Get Connected sessions were first offered in August and will begin in November/December for students who start ARC in Spring 2019.) | Fall 2018 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Scaling in Progress | [Start Right, V.E] |
| 8.26 | Continue to explore the best way to connect with students to provide them with an overview of ARC resources and support and to offer students direction when it comes to course planning. | By Fall 2019 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Scaling in Progress |  |
| 8.27 | Consider, refine, and adopt a proposed approach | Fall 2019 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | n/a | Scaling in Progress |  |
|  | Pathway Community Launch |  |  |  |  |  |
| 8.29 | Establish standard process across all pathway communities for moving students based on changes in area of interest | By Spring 2020 | PES | n/a | Planning to Scale |  |
| 8.30 | Allocate resources to allow setup and launch of pathway communities by Summer 2020 | By Spring 2020 | President’s Executive Staff or designee | n/a | Scaling in Progress |  |
| 8.31 | Train employees who will serve a role in facilitating pathway communities | By Spring 2020 | VPSS, VPI, Deans of Student Services | n/a | Planning to Scale |  |
| 8.32 | Plan and implement pathway presence (e.g., social media presence) | By Summer 2020 | PIO | n/a | Scaling in progress |  |
| 8.33 | Launch pathway communities to students | Summer 2020 | PES, Outreach, Deans of Student Services | n/a | At Scale | Likely to be introduced at the pre-term experience |

Cross-References: #1 - Areas of Interest; #6 – Achieve at ARC Scaling;

9. PEER MENTORING

There is an interest in developing a peer mentoring program utilizing students who have previously participated in the Achieve at ARC experience.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Fully develop a plan for the peer mentoring program and how it integrates with other redesign components | By Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Not Systematic | [IPaSS V] |
| 9.2 | Request program budget | Spring 2021 | VP, Student Services; Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic |  |
| 9.3 | Develop a peer mentor training program | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Not Systematic |  |
| 9.4 | Recruit, select, and train initial group of mentors | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic |  |
| 9.5 | Allocate resources to allow setup and launch of the peer mentor program by Summer 2019 | Summer 2021 | Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic |  |
| 9.6 | Launch peer mentoring | Summer 2021 | Interim Dean, Outreach, FYE, and Pathway Communities | n/a | Not Systematic |  |

Cross-References:

10. PHYSICAL ACCESS AND NAVIGATION: WAYFINDING

An effort is currently underway to improve campus navigation through the use of zones, signage, and other strategies.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Clarify the organizational format (see question below) and make adjustments to the conceptual design if needed | Fall 2018 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.2 | Vet the conceptual design through constituency groups | Fall 2018 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.3 | Make adjustments as needed and finalize conceptual design | Fall 2018 | Director, Administrative Services | Operations Council | Scaling in progress | [Start Right, V.G] |
| 10.4 | Consider, recommend, and adopt conceptual design | Fall 2018 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.5 | Publicize the plan to the campus in preparation for major changes | Spring 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.6 | Contract with vendors as needed to create signage, banners, and other materials | Spring 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.7 | Develop any technology-mediated components (QR codes, etc.) | Spring 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.8 | Create new campus maps for use on the web site and in publications | Spring 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.9 | Install new signage, banners, and other materials; make other changes as planned | Summer 2019/Fall 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.10 | Acquire new photos of the campus | Fall 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.11 | Update the web site and other publications with new images, maps, and descriptions | Fall 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |
| 10.12 | Evaluate effectiveness of wayfinding improvements and refine as needed | By end of Fall 2019 | Director, Administrative Services | Operations Council | Scaling in progress |  |

Cross-References: #24 - Facilities Master Plan

11. PHYSICAL ACCESS AND NAVIGATION: WELCOME & SUPPORT CENTER

Most onboarding services are being moved to a centralized location to create a welcome center for new students.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Consolidate most student services in a centralized location for onboarding | Summer 2019 | VPSS, Deans of Student Services | n/a | Scaling in Progress | [Start Right, V.G] |
| 11.2 | Consider renaming or rebranding areas within the centralized location | Spring/Fall 2019 | VPSS, Dean of Admissions, Dean of Student Support Services, BSO, VPA | n/a | At Scale | [Start Right, V.G] |
| 11.3 | Make adjustments as needed to business processes and staffing in order to facilitate a one-stop model | TBD | VPSS, Deans of Student Services | n/a | Scaling in Progress |  |
| 11.4 | Update website, publications, and other materials to reference the Welcome Center and any renamed areas | Spring/Fall 2019/Ongoing | VPSS, Dean of Student Services | n/a | At Scale |  |
| 11.5 | Communicate the changes to employees with clear directions on how to guide new students | Summer/Fall 2019/Ongoing | VPSS, PIO | n/a | At Scale |  |

Cross-References: #24 – Facilities Master Plan; #20 - Pre-Implementation Work; #10 - Physical Access and Navigation (Wayfinding)

12. FIRST TERM EXPERIENCE (FYE COURSE)

A first term seminar course has been proposed to facilitate retention through community building, academic success strategies, personal development, and other methods. The course could also provide a way to reinforce connections to case management teams (Success Teams) and related supports.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 12.1 | Further explore alternate models offered at other colleges, including those outside of California, to better understand options. In reviewing models, two questions to explore are: - How is the course or non-course experience designed? - What is the intended purpose of the course or non-course experience? | Spring 2021 | Resource Panel via the Student Success Council | SSC | Planning to Scale | [Start Right XII.A; IPaSS VI] |
| 12.2 | Based on exploration, submit a proposal to the Student Success Council that briefly summarizes the models reviewed; recommends an existing or modified model; and indicates next steps necessary for implementation including an estimated timeline. | By Fall2022 | Resource Panel via the Student Success Council | SSC | Planning to Scale |  |
| 12.3 | Implement the model (steps TBD) | TBD pending proposal |  | n/a | [select status] |  |

Cross-References: #8 - Pathways Communities

13. ALTERNATE EXPERIENCE(S) – “NOT NEW” STUDENT

Students who are not considered new to college (such as transfer, re-entry/returning, former advanced education, and others) and need alternate experiences if they are not expected to be directed to and/or served by Achieve at ARC.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Identify groups of incoming students who would not be served by Achieve at ARC or other new student structures | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Not Systematic |  |
| 13.2 | Identify any existing services or onboarding methods used by these students that will be eliminated as a result of the redesign | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Not Systematic |  |
| 13.3 | Design one or more alternate experiences tailored to these student groups. Where possible, integrate with other redesign components such as pathway communities | Spring 2022 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services -Counseling, and Transfer Services; Dean, Student Services – Student Support Services, VPSS | n/a | Not Occurring |  |
| 13.4 | Determine the method to identify these students and invite them into the appropriate experience | Spring 2022 | DInterim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services -Counseling, and Transfer Services; Dean, Student Services – Student Support Services, VPSS | n/a | Not Occurring |  |
| 13.5 | Implement structure necessary to run the proposed experience | Late Spring 2022 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services -Counseling, and Transfer Services; Dean, Student Services – Student Support Services, VPSS | n/a | Not Occurring |  |
| 13.6 | Train those involved in conducting the experience | Early Summer 2022 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services -Counseling, and Transfer Services; Dean, Student Services – Student Support Services | n/a | Not Occurring |  |
| 13.7 | Launch alternate experience for students | Summer 2022 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | n/a | Not Occurring |  |

Cross-References: #6 – Achieve at ARC Scaling; #8 - Pathways Communities

14. TRANSITION SERVICES (Transfer and Career)

As students near completion of their chosen pathway, it is necessary to close the gap between ARC and the next stage of their journey.  Transition services serve as the bridge to ensure ARC students successfully connect with an employer or continue their education at a university.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Assess existing transfer and career services in light of the Redesign and determine opportunities to better serve students as they move beyond ARC | Fall 2020 | Dean, Student Services -Counseling, and Transfer Services; Dean, Student Services – Student Support Services, VPSS | n/a | Not Systematic |  |
| 14.2 | Consider how to expand services based on the role of the newly hired job placement coordinator | Fall 2019 | ????? | n/a | Not Systematic |  |
| 14.3 | Consider potential ways to leverage Pathway Communities for early and continued connection to career possibilities | Fall 2020 | Dean, Student Services -Counseling, and Transfer Services | n/a | Planning to Scale |  |
| 14.4 | Determine desired strategies for improvement and prioritize into a tentative timeline | Spring 2021 | VP, Student Services | n/a | Not Systematic |  |
| 14.5 | Identify any resource needs that are essential to successful implementation of the planned strategies | Spring 2021 | VP, Student Services | n/a | Not Systematic |  |
| 14.6 | Implement the desired changes | Fall 2021 | VP, Student Services | n/a | Not Occurring |  |
| 14.7 | Evaluate effectiveness of the strategies and refine as needed | Fall 2022 | VP, Student Services | n/a | Not Occuring |  |

Cross-References: #8 - Pathways Communities

15. EVALUATION PLAN: EFFICACY OF REDESIGN IMPLEMENTATION

All three reports expressed an interest in assessing components of the redesign implementation.  As students will experience the fully redesigned model, the evaluation plan could be designed to assess the effectiveness of the overall implementation.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 15.1 | Identify questions that need to be answered through the assessment process (desired areas of assessment) | Spring 2021 | Institutional Research Office | n/a | Not occurring |  |
| 15.2 | Draft an assessment plan which addresses the intent of the Student Success Council | Fall 2021 | Institutional Research Office | n/a | Not occurring | See Clarify Program Paths, Start Right, and IPASS reports for considerations |
| 15.3 | Consider, refine, and adopt the assessment plan | Fall 2021 | Institutional Research Office | n/a | Not occurring |  |
| 15.4 | Conduct assessment based on the plan, analyze data, and compile the results | TBD based on plan | Institutional Research Office | n/a | Not occurring |  |
| 15.5 | Consider results and recommendations for improvement | By Spring 2022 | Institutional Research Office | n/a | Not occurring |  |

Cross-References:

16. INTERSECTION WITH DISTRICTWIDE PROCESSES

The following items were recommended but are dependent on the timing and outcome of districtwide processes and/or include an intersection of district and college processes.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 16.1 | Explore splitting summer/fall enrollment periods | Spring 2020 | VPI/VPSS | n/a | At Scale | [Start Right, X.A] This happened in April-June 2020 because of the Covid pandemic and its impacts |
| 16.2 | Acquire and implement a student experience lifecycle solution – Hobsons/HighPoint | TBD – Districtwide |  | n/a | [select status] | [IPaSS IV, VI, IX; Start Right VI.B] |
| 16.3 | Explore adding transaction confirmations to college systems (e.g., registration confirmation) | TBD – Districtwide |  | n/a | [select status] | [IPaSS IX, p. 33] |
| 16.4 | Explore assigning students an email address based on their name rather than student ID | TBD – Districtwide |  | n/a | [select status] | [IPaSS IX, p. 33] |
| 16.5 | Explore development of a student portal | TBD – Districtwide |  | n/a | [select status] | [Start Right p. 12, IPaSS p. 29-31] |
| 16.6 | Automate student-facing business processes | TBD |  | n/a | [select status] | Timeline contingent upon identification of business processes and assessment |

Cross-References: TBD - implications are likely to exist across most other areas due to the breadth of intersections

17. SUPPORTING TECHNOLOGIES: GENERAL EDUCATION SEARCH TOOL

There is an interest in adding a general education course search tool to the college web site to allow students to search for courses by criteria such as general education pattern, CSU/UC transferability, requirements at transfer institutions, themes, interests, and life/career competencies.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 17.1 | Define requirements and desired features | Fall 2018 | New committee TBD | n/a | [select status] | [Clarify Program Paths, Rec. #4] |
| 17.2 | Conduct technical assessment | Early Spring 2019 | Information Technology | n/a | Not occurring |  |
| 17.3 | Design, develop, and test new search tool | By Fall 2019* | Information Technology | n/a | Not occurring | *tentative timeline pending technical assessment |
| 17.4 | Incorporate into college web site | September 2019 | Information Technology, Public Information Officer | n/a | Not occurring |  |
| 17.5 | Launch search tool to students and communicate availability to employees | October 2019 | Information Technology, Public Information Officer | n/a | Not occurring |  |
| 17.6 | Assess and refine tool based on user feedback | Spring 2020 | Information Technology, Public Information Officer | n/a | Not occurring |  |

Cross-References:

18. SUPPORTING TECHNOLOGIES: STUDENT COMMUNICATIONS PLATFORM

There were multiple recommendations related to communications which are likely to require short-term and long-term approaches beyond implementation of Hobsons/HighPoint.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 18.1 | Define short-term requirements and desired features that are immediately needed to supplement Canvas prior to scaling of Achieve at ARC, success teams, and pathway communities | Fall 2018 |  | n/a | [select status] | Districtwide Process for all of these activities. Refer to Starfish Connect efforts |
| 18.2 | Identify short-term solutions that can be quickly implemented with minimal commitment to address defined needs | Spring 2019 |  | n/a | [select status] |  |
| 18.3 | Implement short-term solutions phased to be available as needed by various components | Summer and Fall 2019 |  | n/a | [select status] |  |
| 18.4 | Assess long-term communications technology needs in light of available information on anticipated Hobsons/HighPoint functionality | TBD |  | n/a | [select status] | [Start Right VI.B, VI.C, XIII.F] |
| 18.5 | Recommend a technology master plan that identifies all technologies needed to create a well-integrated communications platform | TBD |  | n/a | [select status] |  |
| 18.6 | Based on the draft plan, recommend a structure for developing and managing student communications incorporating all available technologies | TBD |  | n/a | [select status] | [IPaSS IX, p. 32-33 and 42] |
| 18.7 | Consider, refine, and adopt the technology master plan | TBD |  | n/a | [select status] |  |
| 18.8 | Consider, refine, and allocate resources to the communication structure recommended by the Student Success Council | TBD | President’s Executive Staff or designee | n/a | [select status] |  |

Cross-References: #6 – Achieve at ARC Scaling; #8 - Pathways Communities; #26 – Integrated Planning Improvement; possibly others TBD

19. SUPPORTING TECHNOLOGIES: ALERT AND PROGRESS REPORTING

An effective, technology-enabled early alert and progress reporting system is needed to enable proactive and/or responsive intervention based on analytics, employee observation, and/or student self-reporting.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 19.1 | Identify and/or refine desired functionality and features for early alert, progress reporting, and related coaching/nudges based on predictive analytics or rule-based triggers | Fall 2018 |  | n/a | [select status] | [IPaSS, p. 16, et al.] Refer to District wide process for Starfish early alert. |
| 19.2 | Assess and determine which desirable features and functionality will potentially be met by Hobsons Early Alert; identify any gaps | Spring 2019 |  | n/a | [select status] |  |
| 19.3 | Identify options for meeting gaps (e.g., commercially-available products or estimate of work involved with in-house development) | Summer 2019 |  | n/a | [select status] |  |
| 19.4 | Consider options and recommend solution to supplement or be used in lieu of Hobsons (if needed) | Fall 2019 |  | n/a | [select status] |  |
| 19.5 | Acquire and/or develop the identified solution(s) | Spring 2019 |  | n/a | [select status] |  |
| 19.6 | Implement and train employees on the new solution(s) | Fall 2020/Spring 2021 | AVPSS | n/a | [select status] |  |
| 19.7 | Launch the new solution(s) | Fall 2020 | AVPSS; District | n/a | [select status] |  |

Cross-References: #6 – Achieve at ARC Scaling; #8 - Pathway Communities

20. PRE-IMPLEMENTATION WORK

The following items are necessary steps to facilitate and/or connect the previous components.

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 20.1 | Map and/or diagram how the various components connect together into a holistic student experience | Early Fall 2018 |  | n/a | Planning to Scale | May need separate maps for new students and other student types |
| 20.2 | Establish methods for monitoring and coordination of the various inter-related components of the plan | Early Fall 2018 |  | n/a | Planning to Scale |  |
| 20.3 | Identify leads for each component of the implementation that is not assigned to an existing project team or other entity | Early Fall 2018 |  | n/a | Planning to Scale |  |
| 20.4 | Assess and allocate staffing, facilities, and/or other resources needed to accomplish the implementation plan | Ongoing |  | n/a | Planning to Scale | Clarify Program Paths, IPaSS, and Start Right reports reference resource needs |
| 20.5 | Assign responsibility for holistically assessing the changes needed to employee roles, job functions, and job descriptions across the redesigned student services model | Fall 2018 |  | n/a | Planning to Scale | [IPaSS, p. 17, et al.] |
| 20.6 | Communicate the “big picture” plan to the campus | Fall 2018 |  | n/a | Planning to Scale |  |
| 20.7 | Develop a comprehensive training plan that encompasses all aspects of the redesign and allows training to be staged with the launch cycle | Fall 2018 |  | n/a | Planning to Scale |  |
| 20.8 | Assign responsibility to someone to provide regular campus updates on redesign implementation | Fall 2018 |  | n/a | Planning to Scale | [IPaSS XII] |
| 20.9 | Document the case management model including its purpose, structure, features, and intended benefits | Fall 2018 (first draft) |  | n/a | Planning to Scale |  |
| 20.10 | Conduct business process analysis across student services to assess potential to automate manual tasks | Fall 2018 and ongoing |  | n/a | Planning to Scale | [IPaSS IV, p.17] |
| 20.11 | Determine potential viability of structures such as a first-year instruction and support community of practice based on expected staffing structure and other available interaction mechanisms | By Fall 2019 |  | n/a | Planning to Scale | [IPaSS VII, p. 23-25; IPaSS XII, p. 39] |

Cross-References: Prerequisite to all previous sections (1-22)

21. GOVERNANCE REDESIGN

Governance Framework

| # | Key Activity | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 21.1 | Convene Task Force | 2016-17 | College President; Dean, Planning, Research, and Technology | n/a | At scale |  |
| 21.2 | Develop and adopt Framework | October 2017 | Task Force | n/a | At scale |  |
| 21.3 | Develop operational procedures and systems | Spring 2018 | Dean, Planning, Research, and Technology; designated faculty member | n/a | At scale |  |
| 21.4 | Adopt facilitative leadership and project management techniques | Spring 2018 | Executive Leadership Team | ELT | At scale |  |
| 21.5 | Operationalize framework through training, communication, and other tactics | 2018-19 | Dean, Planning, Research, and Technology; designated faculty member | IEC | At scale |  |
| 21.6 | Institutionalize governance structure with staffing allocation and process refinement | 2019-20 | Dean, Planning, Research, and Technology | IEC | At scale |  |

Cross-References:

22. PROJECT RECOMMENDATIONS (2018-19): ARC ONLINE 2.0

ARC Distance Education Plan (2019-2025)

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
|  | Online Course Scheduling |  |  |  |  |  |
| 22.1a | Utilize the top five online program pathways for year one as identified by Team 2 to develop the foundation for the initial online offerings of the Virtual Education Center | Begin Spring 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.1b | Provide an initial assignment of FTE specifically to the Virtual Education Center for the purposes of developing and offering the courses for the top five programs | Begin Summer 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.1c | Use data (e.g., Ad Astra and education plans) to determine if additional FTE allocation should be considered | Begin Summer 2021 | VPI and AVP’s | SSC | Not Occuring | Dependent on data availability |
| 22.1d | Create a three-year project timeline for Virtual Education Center programs to include both existing programs and those to be developed | Begin Fall 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.1e | Investigate and integrate accelerated learning options to provide timely completion | Begin Fall 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
|  | Online Pathways – Existing Programs |  |  |  |  |  |
| 22.2a | Identify programs by percentage of core courses offered online to establish a threshold percentage for fully online offering potential | Begin Spring 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.2b | Identify online GE courses | Begin Spring 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.2c | Utilize existing department-approved modality-neutral program maps, identify courses offered online and those which are not currently being offered online—including GE | Begin Fall 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.2d | Create fully online program maps which are approved, shared, and advertised | Begin Fall 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.2e | Create an ongoing process to regularly develop and review online program pathways | Begin Fall 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.2f | Recommend that the Program Pathways Committee includes American River College online faculty members | Fall 2020 | VPI | SSC | Not Occuring |  |
|  | New Program Development |  |  |  |  |  |
| 22.3a | Develop a DE focused cyclical mechanism for addressing course and program planning to include improvement, modification, elimination, and additions that align with student and market demand | Begin Spring 2021 | VPI and AVP’s | SSC | Not Occuring |  |
| 22.3b | Develop and offer blueprint templates to aid in the creation of “plug and go” course offerings to encourage rapid development | Begin Spring 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.3c | Investigate and apply Online Competency-Based Education (CBE) | Begin Fall 2021 | VPI and AVP’s | SSC | Not Occuring |  |
| 22.3d | Identify and secure FTE for new course offerings | Begin Fall 2021 | VPI and AVP’s | SSC | Scaling in Progress |  |
| 22.3e | Monitor and analyze the user experience to inform program improvement | Begin Fall 2021 | VPI and AVP’s | SSC | Not systematic |  |
|  | Online Services |  |  |  |  |  |
| 22.4a | Redesign paper-based processes to be inclusive of electronic processes | Begin Spring 2021 | Interim Dean, Outreach, FYE, and Pathway CommunitiesDean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Scaling in Progress |  |
| 22.4b | Improve online communication and access to timely information - College website - Success Team (case management) - Text messaging - Online chat - CCCApply data | Begin Spring 2021; timeline varies by item | Interim Dean, Outreach, FYE, and Pathway CommunitiesDean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Scaling in Progress |  |
| 22.4c | Address technological limitations that inhibit student support | Establish standard and determine needs in 2020-21; allocate resources and implement in 2021-22 | Interim Dean, Outreach, FYE, and Pathway CommunitiesDean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Not systematic |  |
| 22.4d | Bring initial online counseling efforts to scale & across all student services | Establish standard and determine needs in 2020-21; allocate resources and implement in 2020-21 | Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Not occuring |  |
| 22.4e | Offer an alternative virtual option in any American River College business practice that currently requires the student to attend an in-person meeting | Establish standard and determine needs in 2020-21; allocate resources and implement in 2021-22 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Not systematic |  |
| 22.4f | Explore how Los Rios/American River College might extend more support to online students outside of normal business hours | Fall 2020and ongoing | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Not systematic |  |
| 22.4g | Explore how technology might be utilized to create connection and engage online students outside the classroom | Summer 2021and ongoing | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS; VPI, AVPs | SSC | Not systematic |  |
| 22.4h | Develop a student support team model for exclusively online students | Fall 2021and ongoing | Interim Dean, Outreach, FYE, and Pathway CommunitiesDean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Scaling in Progress |  |
| 22.4i | Explore how programs which support disproportionately impacted students can effectively engage online students | Fall 2021and ongoing | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Not occuring |  |

Cross-References: #18 – Student Communications Platform; #8 - Pathway Communities; #2 – Program Roadmaps; #3 – Program Paths Mgmt.; Related Project Work

23. PROJECT RECOMMENDATIONS (2018-19): ENTERPRISE-LEVEL SCHEDULING SOLUTION

March 2019 Project Update

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 23.1 | TBD – no formal recommendations; see March 2019 project update for current status. |  | Project team leads | SSC |  | Districtwide Process for Implementation |

Cross-References: Related Project Work

24. PROJECT RECOMMENDATIONS (2018-19): FACILITIES MASTER PLAN

Final Plan

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 24.1 | Establish and operationalize the campus zone system | TBD | Vice President of Administrative Services | OC | At Scale | #13 Physical Access and Navigation (Wayfinding) |
|  | Major Facility Projects |  |  |  |  |  |
| 24.2a | Technical Education Modernization |  | Vice President of Administrative Services | OC | At Scale |  |
| 24.2b | Corporation Yard Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2c | Stadium Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2e | Davies Hall Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2f | Science Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2g | Welcome & Support Center Modernization/ Expansion | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2h | New Administration Building | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2i | Raef Hall/Future Instructional Space | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2j | Fine Arts Building Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2k | Environmental Resources Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2l | North Parking | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2m | Transit Center & West Parking | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2n | Physical Education Modernization | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2o | Campus Promenade | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2p | Student Quad | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2q | PE Plaza | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2r | Campus Police Building | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2s | Paramedics | TBD | Vice President of Administrative Services | OC | At Scale |  |
| 24.2t | Welcome Loop | TBD | Vice President of Administrative Services | OC | At Scale |  |

Cross-References: #10 – Physical Access and Navigation (Wayfinding); #11 – Physical Access and Navigation (One Stop Welcome Center)

25. PROJECT RECOMMENDATIONS (2018-19): INSTITUTIONAL EQUITY PLAN

Final Plan

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
|  | Setting the Foundation for Equity |  |  |  |  |  |
| 25.1a | Affirm the proposed definitions of equity-related terminology | Summer 2019 | Governance | Approved | Summer 2019 |  |
| 25.1b | Adopt the proposed equity framework and lens | Summer 2019 | Governance | Approved | Summer 2019 |  |
|  | Campus Climate |  |  |  |  |  |
| 25.2a | Focus on welcoming disproportionately impacted communities at ARC | FA 2019 – FA 2020 | Achieve, HomeBases, Learning Communities | HomeBase Implementation Team | FA 2019 – FA 2020 |  |
| 25.2b | Conduct a climate study and a corresponding climate audit that utilizes an equity lens | 2019-2020 | Institutional Research & Disproportionate Impact PT | Preliminary Report(s) | 2019-2020 |  |
| 25.2c | Build institutional capacity in cultural awareness and equity consciousness | 2020-2021 | Office of Equity & Inclusion, CTL, PRIDE Center, UndocuScholar RC | UndocuAlly/Educator Trainings, Safe Space Trainings, Trans Inclusion Trainings, FLEX (Faculty), Common Read | 2020-2021 |  |
|  | Organizational Structure |  |  |  |  |  |
| 25.3a | Cultivate a clear sense of accountability for making institutional equity a priority | 2020-2021 | Office of Equity & Inclusion, Professional Development Project Team, Disproportionate Impact Project Team, Public Information Office, Institutional Effectiveness Council, Operations Council | Equity Framework, Website, PD Project Team recommendations | 2020-2021 |  |
| 25.3b | Foster greater collaboration related to equity issues and interests | 2020-2021 | Led by Office of Equity & Inclusion, CTL & Institutional Effectiveness Council | Annual Unit/Program Planning | 2020-2021 |  |
| 25.3c | Extend transparency | 2020-2021 | President’s Executive Staff and Administrative Leadership Council | Budget Equity Tool | 2020-2021 |  |
|  | Human Resources |  |  |  |  |  |
| 25.4a | Offer training and development to all employees specific to equity and social justice | 2020-2021 | Led by Office of Equity & Inclusion and CTL | FLEX, Convocation, Common Read, Talk It Through Thursdays, Exploring Equity | 2020-2021 |  |
| 25.4b | Nurture the essential conditions to hire and retain people of color | Summer 2020 | Office of Equity & Inclusion, CTL & DO HR | Not systematic | Summer 2020 |  |
|  | Communication |  |  |  |  |  |
| 25.5a | Operationalize the shared definitions, framework, and lens | Fall 2020 | Office of Equity and Inclusion | Added to HTB & ER training, Website, Info sessions | Fall 2020 |  |
| 25.5b | Develop and execute a communication plan focused on equity | 2020-2021 | Office of Equity and Inclusion; PIO; PES | Spirituality Series | 2020-2021 |  |
| 25.5c | Assess and collaboratively revise college guidelines and procedures | Spring 2021 | Office of Equity & Inclusion, Achieve, IEC, Institutional Research |  | Spring 2021 |  |
| 25.5d | Infuse equity communication by leaders throughout the organization | 2020-2021 | PES, ELT, & ALC |  | 2020-2021 |  |
|  | Instruction and Curriculum |  |  |  |  |  |
| 25.6a | Provide faculty with resources to help prioritize curriculum that is inclusive of students from marginalized communities | Ongoing | EAI, EPDP, ITC, & CTL | FLEX; | Ongoing |  |
| 25.6b | Ensure faculty have access to information (data) necessary for promoting the success of students from marginalized communities | SP 2020 | Data On-Demand System, CTL/Institutional Research | Annual Unit Planning/Program Review; EAI Packet, Data on-Demand info sessions; Integrated Planning Portal | SP 2020 |  |
| 25.6c | Sustain and support instructional approaches for supporting students of color | SP 2021 | Office of Equity & Inclusion, CTL, EAI, and EPDP | FLEX, DI Project Teams | SP 2021 |  |
|  | Physical Spaces |  |  |  |  |  |
| 25.7a | Improve physical space to promote success for people with disabilities | Ongoing | Operations & ADA/504 Coordinator | STEM Building | Ongoing |  |
| 25.7b | Equip classrooms with flexible seating configurations | TBD | Operations | [select status] | TBD |  |
| 25.7c | Foster a more welcoming and safe physical environment for transgender and non-binary people | FA 2020 | PRIDE Center & Office of Equity & Inclusion | [select status] | FA 2020 |  |
| 25.7d | Dedicate more space to supporting marginalized students | SP 2021 | Operations Council | [select status] | SP 2021 |  |
| 25.7e | Adapt the physical environment to better support student parents | FA 2021 | CDC? | [select status] | FA 2021 |  |
|  | Student Support |  |  |  |  |  |
| 25.8a | Increase planning and training related to hate and bias incidents | Fall 2020 | The Hub, Equity Advisory Council | Not occurring | Fall 2020 |  |
| 25.8b | Promote collaborative planning at the department/unit-level | TBD | ALC, Institutional Research, PIO | Scaling in progress | TBD |  |
| 25.8c | Expand mental health services focused on marginalized students | SP 2020 | Health & Wellness (DO) | Planning to scale | SP 2020 |  |
| 25.8d | Plan to strategically and comprehensively meet basic needs for students | AY 2020 | CL&D & Student Services, Health & Wellness | Scaling in progress | AY 2020 |  |
| 25.8e | Enhance and increase onboarding efforts for marginalized students | Fall 2019 – Fall 2020 | Achieve & HomeBases (Virtual & Physical) | Not systematic | Fall 2019 – Fall 2020 |  |
| 25.8f | Allocate regular staffing in physical spaces designed for marginalized communities | IN Progress | PES & VPA | Initiated | Fall 2020 | Virtual Black Cultural Center |

Cross-References: Related Project Work; #8 - Pathway Communities; #18 – Student Communications Platform; #24 – Facilities Master Plan; #27 – Wellness Center

26. PROJECT RECOMMENDATIONS: INTEGRATED PLANNING IMPROVEMENT

Integrated Planning Guide (2018-19)

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
|  | Program Review and Unit Planning |  |  |  |  |  |
| 26.1a | Adopt and implement the new program review and unit planning model | Spring 2018 | Executive Leadership Team | IEC | At scale |  |
| 26.1b | Build a new integrated planning system to facilitate the work | By Fall 2018 | Dean, Planning, Research, and Technology or designee | IEC | At scale |  |
| 26.1c | Improve access to data to inform program review | By Fall 2018 | Dean, Planning, Research, and Technology or Designee | IEC | At scale |  |
| 26.1d | Provide training to end users and QuEST | Fall 2018 | Program Review Committee | IEC | At scale |  |
|  | Integrated Planning |  |  |  |  |  |
| 26.2a | Adopt the Integrated Planning Guide | 2019 | Executive Leadership Team | IEC | At scale |  |
| 26.2b | Follow the Multi-Year Planning Calendar to ensure scheduled planning processes are completed | Ongoing | Dean, Planning, Research, and Technology | IEC | Scaling in progress | Appendix A |

Cross-References:

27. PROJECT RECOMMENDATIONS (2018-19): WELLNESS CENTER

Project Report

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
|  | Wellness Center Space |  |  |  |  |  |
| 27.1a | E-Services lab to vacate current location | Spring 2019 | VPSS, AVPSS, Dean of Admissions | OC | At scale |  |
| 27.1b | Repurpose lab for Wellness Center | Spring 2019 | VPSS, AVPSS, Dean of Admissions | OC | At scale |  |
| 27.1c | Move Health Center to new location | Late Fall 2019/Early Spring 2020 | VPSS, AVPSS, Dean of Admissions, Facilities | OC | At scale |  |
| 27.1d | Open new space to campus | Fall 2019 | VPSS, AVPSS, Dean of Admissions, Director of Student Health and Wellness | OC | At scale |  |
|  | Wellness Staff |  |  | OC |  |  |
| 27.2a | Job Description of Wellness Center Coordinator | Spring 2019 | VPSS, AVPSS, Dean of Admissions, Nurses, Consultant | OC | At Scale |  |
| 27.2b | Adjunct Nurse | Fall 2019 | AVPSS, Dean of Admissions | OC | Planning to Scale |  |
| 27.2c | Clerk II (as need upon expansion) | Spring 2019 | AVPSS, Dean of Admissions, Director of Student Health and Wellness | OC | Not Systematic |  |
| 27.2d | Exploration of onboarding partnerships | Spring 2020 | VPSS, Director of Student Health and Wellness | OC | Planning to Scale |  |
| 27.2e | Health Educators | Spring 2020 | VPSS, Director of Student Health and Wellness | OC | Not Systematic |  |
|  | Recommendations Listed Under Lessons Learned |  |  |  |  |  |
| 27.3a | Establish a baseline funding amount to be awarded per academic year | Spring 2020 | VPSS, Dean of Admissions, Fiscal | OC | Planning to Scale |  |
| 27.3b | Utilize the recommended advisory committee and assign members that mirror our campus community | Spring 2020 | VPSS, AVPSS, Dean of Admissions, Director of Student Health and Wellness | OC | Not Occurring |  |
| 27.3c | Provide training to ensure equity is incorporated in the medical services model. | Fall 2019/Spring 2020 | VPSS, Director of Student Health and Wellness, AVPSS, Dean of Admissions | OC | Not Systematic |  |
| 27.3d | Arrange for the team to regularly meet with the assigned district contact employee to participate in contract procedures | Fall 2019/Spring 2020 | VPSS, Director of Student Health and Wellness, AVPSS, Dean of Admissions | OC | Not Systematic |  |

Cross-References:

28. PROJECT RECOMMENDATIONS (2018-19): CLARIFY PROGRAM PATHS

Note: This project team was operational for two years.  The recommendations below are from the 2019 report.  Previous recommendations from the original 2018 report are embedded throughout this document.

Project Report

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 28.1 | Adopt Atlas for managing and publishing program roadmaps | TBD |  | SSC | At Scale |  |
| 28.2 | Review and update program roadmaps annually | Ongoing |  | SSC | Scaling in Progress |  |
| 28.3 | Incorporate program roadmaps in HighPoint Degree Planner | TBD – Districtwide |  | SSC | Scaling in Progress |  |
| 28.4 | Provide professional development | TBD |  | SSC | Not Occuring |  |
| 28.5 | Integrate program roadmaps and areas of interest into other college Guided Pathways redesign work | TBD |  | SSC | Scaling in Progress |  |
| 28.6 | Collaborate districtwide on Guided Pathways design principles | TBD – Districtwide |  | SSC | Scaling in Progress |  |
| 28.7 | Create a Guided Pathways coordinator position | TBD |  | SSC | Not Occuring |  |

Cross-References: #2 – Program Roadmaps; #3 – Program Pathways Mgmt.

29. PROJECT RECOMMENDATIONS: DISPROPORTIONATE IMPACT

AFRICAN AMERICAN, LATINX, NATIVE AMERICAN

Note: This project team focused on three populations: African American (A), Latinx (L), and Native American (N).  The recommendations below are compiled from each of the three reports.

DI Project Team Report

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |

|  | African American |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Clarify the Path: Provide early outreach and financial aid information to prospective and continuing students (A) |  |  |  |  |  |

| 29.1a | Identify/hire/train dedicated Outreach Specialists to collaborate with college and high school staff to provide information on career options, and college programs to prospective high school seniors and their families. | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Scaling in progress |  |
| --- | --- | --- | --- | --- | --- | --- |
| 29.1b | Identify/hire/train dedicated Financial Aid Specialists to provide financial aid information/literacy workshops and financial aid application assistance to prospective high school seniors, their families, as well as, continuing college students. | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Scaling in progress |  |
| 29.1c | Identify/hire/train students to assist in outreach to high schools | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Scaling in progress |  |
| 29.1d | Administer needs assessment to prospective students to determine their financial needs (e.g., financial aid, textbooks, college supplies, necessity to work). | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Scaling in progress |  |
| 29.1e | Collaborate with Career and Pathways Center or Homebases and faculty to administer career assessments, provide labor information and provide career exploration information. | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Scaling in progress |  |
| 29.1f | Deploy financial aid specialist(s) and provide intrusive follow up to African American students three weeks prior to the start of the semester and three weeks after the semester has begun. | Spring 2021 | AVPSS, Supervisor of FA, VPSS | SSC | Scaling in progress |  |
| 29.1g | Include financial aid information in ARC literature and view books targeted to prospective Black and African American students. | Spring 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, AVPSS, VPSS | SSC | Scaling in progress |  |
| 29.1h | Partner with community-based organizations to provide resources and support (e.g. housing assistance and other essential needs) | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communitiess, VPSS | SSC | Scaling in progress |  |

|  | Enter the Path: Provide intrusive, systemic support; create opportunities to increase connections between faculty, staff and students in and out of the classroom (A) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| 29.2a | Utilize integrated Student Success Teams – team members should include: counseling faculty, instructional faculty, peer mentors, tutors, librarians, Student Personnel Specialists, technology specialist, Workforce Development/Internship staff, and a Financial Aid/literacy specialist to provide case management support to students. | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Planning to scale |  |
| --- | --- | --- | --- | --- | --- | --- |
| 29.2b | Create Black Faculty and Staff Advisory Council to provide advisement on issues regarding Black and African American student success and student needs. | Spring 2021 | Dean of Equity and Inclusion | SSC | Planning to scale |  |
| 29.2c | Identify a dedicated space with budget and staffing for Black and African American students to build community, access resources, affirm identity and cultivate connections between students, staff and faculty. | Spring 2021 | Dean of Equity and Inclusion | SSC | Planning to scale |  |
| 29.2d | Utilize Starfish or other comparable technology, to create warm hand-offs, positive reinforcement, referrals to people via technology. | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, AVPSS, VPSS | SSC | Planning to scale |  |
| 29.2e | Expand course offerings of GE courses with an African American emphasis taught by equity minded, culturally responsive faculty | Fall 2021 | VPI, ,AVP’s, Deans | SSC | Not systematic |  |
| 29.2f | Publish annually in print or electronically a directory of ARC Black and African American faculty and staff members and disseminate to new students. | Fall 2021 | PIO | SSC | Planning to scale |  |
| 29.2g | Increase the capacity of Umoja Sakhu and/or other programs and services which focus on positive racial identity development through curriculum as well as programming and services. | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Not systematic |  |
| 29.2h | Expand course offerings with an African/African American emphasis, taught by equity minded faculty who utilize culturally responsive teaching practices. | Fall 2021 | VPI, ,AVP’s, Deans | SSC | Not systematic |  |
| 29.2i | Disseminate Welcome Letter with links to resources, services, programs, BFS Directory, to all new students who identify as Black or African American | Fall 2021 | PIO | SSC | Planning to scale |  |

|  | Stay on the Path: Provide funding resources, leadership and employment opportunities for students to alleviate their financial burden (A) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| 29.3a | Identify/hire/train Instructional Assistants, Student Personnel Assistants, student assistants, peer mentors, tutors and technology aids; embed them in classes and offer follow-up academic assistance to students. | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities, VPSS | SSC | Planning to scale |  |
| --- | --- | --- | --- | --- | --- | --- |
| 29.3b | Collaborate with Workforce Development and Internship Program to identify funding sources, provide stipends for internships and employment opportunities. | Fall 2021 | AVP Workforce | SSC | Not systematic |  |
| 29.3c | Dedicate funds, administered by an advisory board, to supply students with funding for textbooks, college resources and other essential needs. | Fall 2021 | Interim Dean, Outreach, FYE, and Pathway Communities; Dean, Student Services – Counseling and Transfer Services; Dean, Student Services –Student Support Services, VPSS | SSC | Planning to scale |  |
| 29.3d | Create technology loan programs. | Fall 2021 | Dean of Library and Learning Resources,, VPSS | SSC | Planning to scale |  |

|  | Ensure Learning: Enhance classroom learning environments and invest in instructor/educator training resources that promote collectivism, culturally responsive teaching practices and other equity approaches that help students learn. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| 29.4a | Invest in teacher training programs like those offered by the Association of College and University Educators (ACUE) and the Center for Organizational Responsibility and Advancement (CORA) to encourage, support and assist faculty in learning effective teaching strategies. | Fall 2021 | Dean of Equity and Inclusion | SSC | Planning to scale |  |
| --- | --- | --- | --- | --- | --- | --- |
| 29.4b | Initiate cross-talk opportunities for students, staff and faculty to connect | Fall 2021 | Dean of Equity and Inclusion |  | Planning to scale |  |
| 29.4c | Embed staff such as Instructional Assistants, Student Personnel Assistants, tutors, and student technology assistants in classes. | Fall 2021 | VPI, AVP’s |  | Planning to scale |  |
|  | Latinx |  |  |  |  |  |
| 29.5 | Finalize the analysis of the DI survey | Fall 2020 | Dean of Research & Planning | IEC | Planning to scale |  |
| 29.6 | Treat this project as iterative |  |  | SSC | Planning to scale |  |
|  | Students first: Consider students first AND remember our interaction is because they have come to be students, but that’s not all who they are: they are people who want to learn and get (better) jobs; they are not customers; teach students to be students if they need that help; see more of the person who students are |  |  |  |  |  |
| 29.7a | Communicate support |  |  | SSC | Planning to scale |  |
| 29.7b | Involve Parents/Families |  |  | SSC | Planning to scale |  |
| 29.7c | Allocate dedicated space for Latinx students to study, get counseling and personal/career advice, do extracurricular activities, receive tutoring, relax, be affirmed, inspired, and decrease isolation |  |  | SSC | Planning to scale |  |
| 29.7d | Provide confidential space for students who are undocumented/have mixed status family members and LGBTQ students to discuss personal, legal matters |  |  | SSC | Planning to scale |  |
| 29.7e | Install gender neutral bathrooms in each building |  |  | OC |  |  |
| 29.7f | Improve financial resources, such as emergency funds, for undocumented, mixed status, Latinx students |  |  | SSC | Planning to scale |  |
| 29.7g | Provide earlier outreach, orientation for Latinx students including collaboration with high school partners. Suggested strategies include hiring bilingual English/Spanish staff for this work |  |  | SSC | Planning to scale |  |
| 29.7h | Clarify the Pathways |  |  | SSC | Planning to scale |  |
| 29.7i | Provide specialized tutoring for Latinx students such as hiring former PUENTE students |  |  | SSC | Planning to scale |  |
| 29.7j | Expand legal services to undocumented students and students from mixed status families as well as LGBTQ Latinx students |  |  | SSC | Planning to scale |  |
| 29.7k | Institute Latinx welcome activities each semester with a focus on academics. |  |  | SSC | Planning to scale |  |
| 29.7l | Support student-led research (Community Action Research or Community Participatory Research) |  |  | SSC | Planning to scale |  |
| 29.7m | Provide student-led research presentation opportunities |  |  | SSC | Planning to scale |  |
| 29.7n | Expand summer course offerings, (ex. PUENTE-affiliated courses) |  |  | SSC | Planning to scale |  |
| 29.7o | Institute PUENTE or HSI-related Summer Bridge |  |  | SSC | Planning to scale |  |
| 29.7p | Fund more work study positions for Latinx students |  |  | SSC | Planning to scale |  |
| 29.7q | Launch programs for neglected groups, including formerly incarcerated students |  |  | SSC | Planning to scale |  |
|  | Systems second: Change the system to fit the student instead of trying to change the student to fit the system |  |  |  |  |  |
| 29.8a | Continue to build “culture of equity” within professional development that includes examining inequities within participants’ departments |  |  | SSC | Planning to scale |  |
| 29.8b | Institute faculty inquiry groups–whose members engage in examining inequities in their departments |  |  |  |  |  |
| 29.8c | Involve national experts on race in higher education in the training of faculty |  |  |  |  |  |
|  | Mentor and train faculty to teach better |  |  |  |  |  |
| 29.9a | Implement recommendations from Professional Development and Training Plan Project Team |  |  | SSC | Planning to scale |  |
| 29.9b | Work with Center for Teaching and Learning to reimagine and implement more culturally relevant and trauma-informed pedagogical approaches. Refer to the team report for suggested strategies. |  |  |  |  |  |
|  | Increase Support Latinx Employees: Prioritize recruiting, hiring, and retaining bicultural, bilingual Spanish-speaking Latinx and equity-minded staff, faculty, and administrators to attain parity with the Latinx student body, starting with Latinx Outreach Officer |  |  |  |  |  |
| 29.10a | Support the recruitment, hiring, and mentoring of Latinx employees. |  |  | SSC | Planning to scale |  |
| 29.10b | Retain Latinx staff, faculty, and administrators |  |  |  |  |  |
| 29.10c | Incentivize mentoring/training for all new adjunct and tenure track faculty |  |  |  |  |  |
| 29.10d | Incentivize mentoring/training for tenured faculty |  |  |  |  |  |
| 29.10e | Revise evaluations of faculty so they are focused on faculty’s teaching not students’ performance |  |  |  |  |  |
| 29.10f | Require accurate culturally reflective and relevant curriculum |  |  |  |  |  |
| 29.10g | Provide students the opportunity to submit anonymous evaluations of faculty and staff in writing and online |  |  |  |  |  |
| 29.10h | Provide students the opportunity to submit anonymous evaluations of administration in writing and online. |  |  |  |  |  |
| 29.10i | Clarify rewards for positive evaluations and consequences for negative evaluations for administration, faculty, and staff |  |  |  |  |  |
| 29.10j | Publicize process for students to report complaints against administration, faculty, and staff |  |  |  |  |  |
| 29.10k | Ensure that students are not retaliated against for complaints against administration, faculty, and staff |  |  |  |  |  |
| 29.10l | Create ombuds resource to advocate for students or assist students when they advocate for themselves |  |  |  |  |  |
| 29.10m | Recognize all employees are educators |  |  |  |  |  |
| 29.10n | Recognize that students may confide in non-faculty, non-counselors, non-program specialists, etc. (ex. facilities staff) |  |  |  |  |  |
| 29.10o | Provide process for non-faculty, non-counselors, non-program specialists, etc. (ex. facilities staff) to communicate concerns shared by students to appropriate college personnel |  |  |  |  |  |
| 29.10p | Offer free citizenship classes to all Latinx workers and families |  |  |  |  |  |
| 29.10q | Offer free classes to classified part-time Latinx workers and families |  |  |  |  |  |
| 29.10r | Do anonymous exit interviews and use the results for actions such as to prevent more loss of employees and to change practices as needed to retain employees |  |  |  |  |  |
| 29.11 | Enhance communication between La comunidad de ARC and Executive Leadership Team |  | President | ELT | Planning to scale |  |
| 29.12 | Increase La comunidad de ARC collegewide representation in governance groups |  | President | ELT | Planning to scale |  |
| 29.13 | Achieve Hispanic Serving Institution (HSI) status and write a grant with regular input and feedback from a grant implementation team including representation from Latinx employees | Fall 2020 | Dean of Research & Planning | SSC | Planning to scale |  |
|  | Native American |  |  |  |  |  |
|  | Begin the shift to a Sovereignty Frame by recognizing the implications | Spring 2021 | President | SSC | Planning to scale |  |
| 29.14a | ARC must acknowledge its historical relationship to the land that it occupies. |  |  |  |  |  |
| 29.14a | ARC should form executive-level MOU’s with local tribes to establish reciprocal relationships and unique services for citizens of those nations. |  |  |  |  |  |
| 29.14a | ARC should create the administrative capacity to establish and maintain relationships with the tribes represented by its American Indian students. |  |  |  |  |  |
| 29.14a | ARC should build out support systems for citizens of tribal nations that take into account Federal and State Indian law; historic discrimination against citizens of tribal nations based on tribal status; K-12 Indian Education, Tribal TANF, Native American Health Centers, the Indian Child Welfare Act, the Native American Graves Protection and Repatriation Act, and the Native American Religious Freedom Act. |  |  |  |  |  |
| 29.14a | ARC should systematically and in broad strokes employ a sovereignty frame that may inform and enrich instruction, operations, construction, planning, and hiring. |  |  |  |  |  |
| 29.15 | Establish an Office of Tribal Relations | Spring 2021 | President | SSC | Planning to scale |  |
|  | Continue and expand direct American Indian and Native American student support |  |  |  |  |  |
| 29.16a | The Campus (refer to team report for suggested strategies) |  |  | SSC | Planning to scale |  |
| 29.16b | The Classroom (refer to team report for suggested strategies) |  |  | SSC | Planning to scale |  |
| 29.16c | The Self (refer to team report for suggested strategies) |  |  | SSC | Planning to scale |  |
| 29.16d | The Community (refer to team report for suggested strategies) |  |  | SSC | Planning to scale |  |

Cross-References:

30. EDUCATION MASTER PLAN: GUIDING IMPERATIVES

Note:

Project Report

| # | Imperative | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 30.1 | Close the opportunity gap: ARC Response Summary: Holistically, ARC will close the opportunity gap across all stages of the student lifecycle by 2031. The college will continue its existing redesign efforts and demonstrate measurable improvement in outcomes for historically underserved students. It also should work towards actualizing the recommendations of the Institutional Equity Plan and strengthening relationships with communities of color in order to create a more equitable, collaborative, and inclusive institution. ARC may seek growth by expanding access and broadening its reach to areas and populations that have not been fully served in the past. It should respond to the unique role of the community college by ensuring that students have access not only to education, but to the basic life necessities that are a prerequisite to participation. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.2 | Prepare students for an ever-changing landscape of work: ARC Response Summary: Across its programs, the college will offer a wide range of opportunities for rapid reskilling and skill advancement to support individuals as they navigate career transitions, self-employment, and an increasingly technology-enabled workplace. ARC will promote basic technology competency among all students, as well as offering technical training in emerging technologies. Emphasis should be given to mitigating inequities in worker displacement by providing a path to re-employment in fields with a median living wage and secure job outlook. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.3 | Integrate essential skills: ARC Response Summary: The college will empower future students, as well as employees, and enrich its community by developing well-rounded and increasingly resilient individuals who possess a practical blend of technical and essential skills that can be applied throughout life. Creative methods should be utilized to expose students, irrespective of program length, to educational experiences that develop essential skills. ARC should intentionally bond disciplines identified as transfer-oriented and workforce preparation through curricular integration and faculty interaction. It should also ensure that all students, regardless of socio-economic background, are encouraged to grow and expand their capacity to contend with ambiguity, complexity, diversity, and change. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.4 | Tailor experiences to the individual: ARC Response Summary: The college experience will be tailored to fit the student, rather than expecting the student to fit into a standardized college model. ARC can expand access to education by increasing flexibility and reducing institutional constraints. It will disrupt the academic calendar and eliminate barriers to enrollment by providing a viable option that is attractive and accessible to a variety of students. Through a blend of human interaction and technological tools, ARC will extend a level of personalization that recognizes students as individuals and inspires them towards goal completion. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.5 | Strengthen connections with employers: ARC Response Summary: The college will strengthen connections to employers and create a pipeline of skilled employees that are prepared based on current industry specifications. ARC will strive to minimize institutional barriers and become the preferred training partner of employers in the region. It will facilitate frequent interaction between employees, industry professionals, business associations, and non-profit organizations to ensure that ARC programs are in sync with employer needs. It should also work with its employer partners to minimize barriers in the workplace that may inhibit the future employment and success of marginalized populations. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.6 | Stimulate exemplary teaching and learning: ARC Response Summary: Faculty will be encouraged and supported to stay at the forefront of their craft through exploration of learning science, emerging technologies, and other frontiers that have the potential to progressively develop instructional excellence. ARC should stimulate exemplary teaching and learning by embracing a forward-thinking approach to how it delivers education and providing resources that enable the use of equitable methods. It will strive for excellence by pushing boundaries to foster engaging and equitable education. The physical and virtual classrooms should be reimagined to ensure they are ideally suited to changing andragogy. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.7 | Adapt the physical campuses: ARC Response Summary: The institution will evolve its physical campuses based on future needs, rather than current realities. ARC will strive to make its facilities more inclusive and accessible. It will be aspirational as it plans for changes in how the campus will be used by students as well as the increasing technology and energy demands. It should gravitate towards greater flexibility in space design and heightened environmental stewardship. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.8 | Achieve operational effectiveness: ARC Response Summary: The college will achieve operational effectiveness by aggressively seeking to modernize its own practices and stripping away clunky methods that inhibit employees from doing their best work. In alignment with its existing strategic goals, it will actively pursue “proactive, effective, and efficient operational systems.” ARC will provide leadership in identifying and renovating antiquated or ineffective practices that are a barrier to the success of marginalized populations. It will further develop its organizational agility by fostering an entrepreneurial culture and community service orientation that consistently innovates as well as enabling effectiveness through professional growth of its employees. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.9 | Cultivate financial sustainability: ARC Response Summary: ARC will continuously develop and maintain financial sustainability to enable achievement of its mission and strategic goals. While retaining its core focus that places students first, the college will strategically leverage the incentives of performance-based funding to capture resources with which it can cover the ongoing cost of education. ARC should also diversify revenue streams and augment its funding sources in order to maintain an exemplary learning environment that engages students and provides employees with the best tools available. Through its efforts to streamline organizational practices, the college will endeavor to reduce costs and deploy its resources wisely | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |
| 30.10 | Bolster advocacy, collaboration, and coordination: ARC Response Summary: The college will remain keenly aware of the higher education landscape in which it exists and use its influence to promote equity-minded education. It will position itself to take advantage of, rather than be subject to, the shifts within the California Community Colleges system and the regulatory structure under which it operates. ARC will further develop its capacity to advocate and coordinate effectively in order to accomplish its mission. It will seek new ways of collaborating across the district in order to become a more nimble organization and develop a unified voice with which to promote shared interests. Recognizing the evolving nature of its environment, ARC should develop its ongoing relationships with external stakeholders to understand the changes that are most likely to occur in the region and how ARC needs to adapt. It will amplify its existing partnerships with K-12 districts, universities, and other stakeholders. | Fall 2031 | VPI, AVP’s, Deans | SSC | Planning to scale |  |

Cross-References:

31. PROJECT RECOMMENDATIONS: PROFESSIONAL DEVELOPMENT AND TRAINING

Note:

Project Report

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 31.1 | Consider the resources that may be needed for implementation as part of the budgeting process for 2020-21 | Fall 2020 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.2 | Allocate personnel for the 2020-2021 academic year [see Essential Conditions for Professional Growth] | Fall 2020 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.3 | Have a dialogue in Administrative Leadership Council (ALC) about how the management team can foster an affirmative management culture that better enables and encourages employees to participate in professional development as part of their expected job duties [see Essential Conditions for Professional Growth] | Fall 2020 | President’s Executive Staff | IEC | Planning to scale |  |
| 31.4 | Ask PES to consider how to address the essential condition of Ample Time for the 2020-2021 academic year [see Essential Conditions for Professional Growth] | Fall 2020 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.5 | Share the general vision for professional development and orient college employees to the new competency-based model | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.6 | Ensure professional development can be flexibly delivered to accommodate employees in campus and remote environments | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.7 | Redesign and furnish the ITC as an accessible, innovative, well-known space for informal gathering, formal learning, just-in-time learning, large group learning, small group learning, and one-on-one learning [see Essential Conditions for Professional Growth] | Spring 2021 | Dean of Equity and Inclusion and Vice President of Administrative Services | IEC | Planning to scale |  |
| 31.8 | Move the Center for Teaching and Learning (CTL) to the ITC | Spring 2021 | Dean of Equity and Inclusion and Vice President of Administrative Services | IEC | Planning to scale |  |
| 31.9 | Host a naming contest to rebrand the CTL and ITC into a new professional development entity that reflects the future vision | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.10 | Form an advisory committee for Professional Development to provide input and guidance [see Essential Conditions for Professional Growth] | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.11 | Continue the listening sessions begun in Spring 2020 to further inform the advisory committee | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.12 | Create and hire the permanent CTL Co-Director positions [see Essential Conditions for Professional Growth] | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.13 | Over a two-year period, implement the first phase of professional development focused on the competencies of Equity-Minded Service, Effective Communication, and Organizational Adeptness. Three components are proposed to address foundational knowledge, practical knowledge, and inquiry levels | Spring 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.14 | Modify the flex reporting system to incorporate the new competency-based model | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.15 | Work with the existing professional development committees to incorporate the competencies into their processes (e.g., consideration of requests for funding) | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.16 | Develop a standardized employee onboarding curriculum that would be relevant and immediately beneficial to all new employees regardless of role | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.17 | Develop portfolio of regularly scheduled Level I trainings including online, self-paced modules | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.18 | Prompt further dialogue once the full analysis of the Institutional Campus Climate Survey is complete; in particular, consider the disaggregated results of the questions in the professional development section of the employee survey | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.19 | Budget $26,000 annually for professional development of the Co-directors, Faculty Coordinators, and Staff Liaison. It is critical that the facilitator expertise and skills be supported and maintained. Facilitators should have the capacity to approach all professional development through an equity lens and through the principles outlined in ARC’s Commitment to Social Justice and Equity; Institutional Equity Plan; and the Educational Master Plan. | Fall 2020 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.20 | Create a system to ensure stakeholders provide regular input and feedback because it is critical that those who are served by professional development have a voice in its development and delivery. | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.21 | Incorporate foundation-level training into department and committee work | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.22 | Grant access to connect professional development personnel to Annual Unit Plan reporting of professional development requests | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.23 | Assess the college’s professional development needs through existing structures like Annual Unit Plans and connect departments’ needs to the competencies. | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.24 | Implement individual professional growth plans supported by technology that fosters use (e.g., badging or gamification) | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |
| 31.25 | Reassess the competencies and update if needed during the next scheduled planning cycle identified in the ARC Integrated Planning Guide (currently scheduled for 2027) | Fall 2021 | Dean of Equity and Inclusion | IEC | Planning to scale |  |

32. PROJECT RECOMMENDATIONS: STRATEGIC ENROLLMENT MANAGEMENT

Note: Finalized in Fall 2020

Project Report

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 32.1 | Develop standing Strategic Enrollment Management team to monitor enrollment data, rubrics, and procedures. | Fall 2020 | VPI, AVP’s | SSC | Planning to scale |  |
| 32.2 | Hire support staff to facilitate maintenance of Ad Astra Platinum system, interface between data on demand system (research office), and coordination with other technical solutions (Highpoint, Starfish, et cetera.) | Spring 2021 | VPI, AVP’s | SSC | Planning to scale |  |
| 32.3 | Work with District IT to build out six development schedules in PeopleSoft: Fall Odd-Years Fall Even-Years Spring Odd-Years Spring Even-Years Summer Odd-Years Summer Even-Years | Spring 2021 | VPI, AVP’s | SSC | Planning to scale |  |
| 32.4 | American River College needs a centralized system to track external FTEF (grants) that fund sections, instructional FTEF used to support coordinators and other work of the college, and other programs that are scheduling sections in addition to division offices (e.g. the Advanced Education program). | Spring 2021 | VPI, AVP’s | SSC | Planning to scale |  |

33. PROJECT RECOMMENDATIONS: SUSTAINABILITY IMPROVEMENT

Note:

Project Report

| # | Recommendation | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- | --- |
| 33.1 | Institutionalize a sustainability program, establish an Office of Sustainability, and increase funding for sustainability | Summer 2020 | Director Ops/Sustainability-Designee | Operations Council | Completed | Campus Operations has changed its name to Campus Operations and Sustainability |
| 33.2 | Develop a communication plan for public relations and events and outreach around sustainability | Fall 2020 | Director Ops/Sustainability/PIO | Operations Council | on going | ARC does not have an official social media presence or channel to interface with the public or the ARC community on sustainability. To improve visibility and education around climate change and sustainable practices, ARC needs to engage the public via media outlets, social media, public outreach, and events. |
| 33.3 | Evaluate and enhance sustainable practices in current and future built environment, design new buildings to meet GSA and LEED sustainable design criteria, advocate for sustainable policies and practices, and operational and maintenance practices of existing and future environments | Summer 2020 | Facilities Management | District Office/FM | on going | New buildings, such as the Diane J. Bryant STEM Innovation Center, are designed to be more sustainable than baseline requirements. ARC has invested in upgrading the hydronic lines to be more efficient in delivering cooling and heating to current and new buildings. The project will reduce energy consumption and improve heating efficiency while reducing environmental impact. ARC does not have direct control over these practices, however ARC will continue to advocate with the district. |
| 33.4 | Transition to environmentally friendly foodservice products and materials, influence our community and foodservice vendors, increase composting, and advocate for sustainable policies. | Fall 2020 | Director Ops/Sustainability/Vendors | Director Ops/Sustainability/Vendors | on going | ARC provides food services via contracted vendors and via The Oak Cafe. Biodegradable straws are used in The Oak Cafe Bakery and dining room. The Oak Café is a culinary program offered by Fine and Applied Arts, which focuses on student training in the food industry. Contracted vendors via the student center, bookstore, and other vending sources located around the campus provide food services to the general campus. |
| 33.5 | Organizational/leadership/faculty training, curriculum, making connections, in (and beyond!) the classroom, and hiring practices. | Fall 2020 | Vice President of Instruction/Ops | Operations Council | on going | Although there are some programs and courses that explicitly focus on sustainability, climate change, and environmental conservation, ARC does not emphasize these themes throughout its academic programs. Faculty typically have the closest connection to our students, and so have the opportunity and obligation to be leaders and communicators and to form an important bridge between our students and other faculty, campus staff, and administration. |
| 33.6 | Assess and enhance climate control practices, support ARC community and the student population, electrify campus fleet, public transportation infrastructure, and improve campus infrastructure to meet current and future demands | Spring 2021 | Director Ops/Ops Supervisor | Operations Council | ongoing | To address the effects of climate change and be a proactive citizen of Earth, ARC is doing its part in reducing its reliance on fossil fuels and embracing sustainable technologies. Many areas on campus still rely on fossil fuels and there are gaps in our understanding of building energy utilization. However, ARC has invested in many technologies to reduce energy consumption such as motion-activated lighting in buildings and occupancy thermostats that control the demand for air conditioning and heat. All of the energy used by ARC comes from renewable sources reducing the demand for fossil fuels. The most effective way to reduce environmental impact and reduce greenhouse emissions generated via commuting is to adopt public transportation. Public transportation enables disproportionately impacted communities to access resources, reduce traffic congestion on highways and streets, preserve open spaces, and enable our communities to be mobile and healthy. ARC’s Oak Café promotes environmental stewardship by purchasing produce from local farms thereby reducing emission generated by long-distance transportation of produce |
| 33.7 | Increase the use of native plants, effective landscape management, and collaboration and restoration of native areas project. | Fall 2020 | Director Ops/Sustainability-Designee | Operations Council | in process | Within the Facilities Master Plan, ARC has developed design guidelines for incorporating and increasing the use of native plants, effective landscape management as well as creating and maintainaing green spaces on Campus. American River College has received the designation of Tree Campus USA. This reflects ARCs dedication to creating and maintaining green spaces that provide many health and wellness benefits to the ARC community. To continue ARCs Tree Campus USA designation, the ARC community must work to embrace green solutions, use native species throughout its landscapes, and seek to enhance native habitats in its periphery. |
| 33.8 | Continue current efforts to recycle, reduce, and reuse, continue building on our commitment, and create policies and collaborate with California Community Colleges. | Summer 2020 | Director Ops/Sustainability-Designee | Operations Council | on going | We have increased efforts to divert waste from the landfill and created a waste reduction advisory committee district-wide (R-8371). This effort includes recycling, reduction and reuse of materials that continues today. The Oak Café uses a tiered waste system. This includes recycling and food waste. The use of these is reviewed in culinary and work experience courses. ARC waste streens are segregated based on their site of generation, such as Green Waste, Wood Waste, Recycled Waste, Food Waste, Metal Bin, Universal Waste, Landfill Waste, Hazardous Waste, Construction Waste, Surplus |
| 33.9 | Reduce potable water consumption, modification of delivery systems, and increase access to clean water. | Fall 2019 | Director Ops/Sustainability-Designee | Operations Council | on going | To alleviate the demand on potable water, ARC installed water stations throughout the campus. These stations have already saved countless plastic bottles. However, the campus is unable to accurately track how the stations are being used with exception to the smart fill station, which tracks water usage. The Oak cafe has filtration systems for the water served in the café reducing the need to buy bottled water. ARC has also invested in efficient flush toilets and under-sink water heaters that deliver instantly hot water reducing water waste. |

RELATED PROJECT WORK (2019-20)

The following work has already been authorized, assigned to a project team, and is being carried out under the specifications of an adopted project charter.  Additional recommendations may emerge from these Please visit IGOR or the ARC Website for the charters of current teams.

| Project | Timeline | Title or Role | Council | Status | Notes/References |
| --- | --- | --- | --- | --- | --- |
| Educational Master Plan | 2019-20 | Project leads | SSC | Scaling in Progress |  |
| Strategic Enrollment Management Plan | 2019-20 | Project leads | SSC | Scaling in Progress |  |
| Professional Development and Training (as part of an Employee Development and Retention Plan) | 2019-20 | Project leads | IEC | At scale |  |
| Sustainability Improvement | 2019-20 | Project leads | OC | [select status] |  |
| DI Populations | 2019-20 | Project leads | SSC | Scaling in Progress |  |

REFERRED TO OTHER PROCESSES

| Component | Refer Recommendation To | Rationale |
| --- | --- | --- |
| Outreach-focused information web site [Start Right VI.A] | Strategic Enrollment Management (SEM) Plan project team | Consider within the context of a broader strategy for enrollment management efforts to create a cohesive approach |
| Outreach communications highlighting benefits of ARC [Start Right VI.F] | Strategic Enrollment Management (SEM) Plan project team | Consider within the context of a broader strategy for enrollment management efforts to create a cohesive approach |
| Enhance pre-onboarding communications [Start Right VI.H] | Strategic Enrollment Management (SEM) Plan project team | Consider within the context of a broader strategy for enrollment management efforts to create a cohesive approach |
| User-centered and accessible web design [IPaSS IX, p. 28] | Operations Council; Student Success Council | Consider from both the technical and student success perspectives to consider IPaSS concerns and develop full recommendation for changes in practice |
| Equity training [Start Right VIII.A] | Institutional Equity Plan project team; Professional Development and Training project team | The institutional equity plan is expected to establish the framework for equity training which can then be addressed in an institutional professional development plan. |
| Other training [Start Right VI.E, VIII.B, VIII.C, VIII.D, IPaSS X, p.17,34-35 ] | Professional Development and Training project team | Consider within the context of all professional development to create a cohesive set of offerings |
| Low-cost/no-cost textbooks [Start Right XIII.C] | Faculty/Academic Senate | Adoption of specific textbooks for each course is determined by the faculty |
| Reexamine general education [Clarify Program Paths, Rec. #4] | Educational Master Plan project team (future) | See “Reexamining General Education” in the Clarify Program Paths report for rationale. Consider within the broader context of the future direction of the college. |