Project Team:	HomeBase Implementation Review Team

Project Type:  Resource Panel

Project Duration: Fall 2021

Sponsoring Council:  Student Success Council

PROJECT BACKGROUND AND NEED	(Why is the project necessary?)

American River College formed an implementation team at the beginning of 2020 to guide development of HomeBase pathway communities. In March, Los Rios facilities were closed and ARC transitioned to remote operations due to the COVID-19 pandemic. The team recommended placing physical HomeBases temporarily on hold so that focused attention could be given to the creation of a virtual HomeBase presence.  Virtual HomeBases were implemented during the Fall 2020 semester, and have continued to grow.

PROJECT PURPOSE AND SCOPE (What is the project expected to encompass? What are the boundaries?)

The purpose of this project is to provide an assessment of the implementation of Virtual HomeBases and recommendations for moving forward.

Implementation Review shall be held to the following boundaries:

- The review shall focus on the questions posed through the Project Objectives.

PROJECT OBJECTIVES (What is the project expected to achieve?)

Successful completion of this project is intended to answer the following questions:

Assessment of HomeBase Questions:

- What is the current structure and staffing for HomeBase?

- What activities occurred in the HomeBases since August 2020?

- What was the level of student engagement in the HomeBase?

- What was the level of faculty engagement in the HomeBase?

- What student services were provided to students through HomeBase?

- What instructional services were provided to students through HomeBase?

- What is the alignment between Area Offices, Area Deans, and HomeBases?

Recommendations for HomeBase Questions:

- What is the recommended structure and staffing for HomeBase?

- What are recommended yearlong activities for HomeBase?

- What is the recommended level of student engagement in the HomeBase?

- What is the recommended level of faculty engagement in the HomeBase?

- What is the recommended level of student services through HomeBase?

- What is the recommended level of instructional services through HomeBase?

- What is the recommended alignment between Area Offices, Area Deans, and HomeBases?

PROJECT DELIVERABLES (What items will be produced during the project?)

Deliverables to be completed and/or submitted for approval:

- Assessment of implementation of Virtual HomeBases.

- Recommendations for moving forward.

SUCCESS INDICATORS (How will success be measured or determined?)

The project will be considered successful when:

- Final document with project deliverables is presented to the Student Success Council

All of these indicators can be thoroughly accomplished through completion of the stated project objectives.

PROJECT ASSUMPTIONS (What conditions are believed to exist?)

The project team was authorized based on the following assumptions:

An assessment of HomeBase implementation is an important element that will guide future decisions regarding both HomeBase and the College’s organizational structure.

PROJECT RISKS, CONSTRAINTS, OR DEPENDENCIES (What factors might impact the project?  How might the project intersect with the internal or external environment including other projects?)

The project team should be aware of the following known risks, constraints, and/or dependencies:

- The implementation of Virtual HomeBases was done during the pandemic, creating challenging implementation issues.

OTHER CONSIDERATIONS (What are the anticipated implications related to equity and inclusion; research and data; district policies and regulations; district and/or college-wide practices; college-wide cross-functional relationships; and resource needs such as staffing, workload, technology, and space/facilities?)

PROJECT TIMELINE/KEY MILESTONES

| Month(s) | PROJECT PHASE | FOCUS/MAJOR TASKS |
| --- | --- | --- |
| Fall 2021 | Initiation | Project initiation and charter development |
| Fall 2021 | Preparation | Project planning; team scheduling; initial research and discovery; preparation for kickoff |
| Fall 2021 | Team-Based Work | [will vary by project; should identify any key milestones] |
| Fall 2021 | Formal Review | Review and adoption of deliverables through governance processes |
| Spring 2022 | Closure | Celebrate the project team’s work and archive artifacts of the project |

Planned Governance Flow of Deliverables

| Meeting Date | Council | Desired Outcome |
| --- | --- | --- |
| November 16, 2021 | Student Success Council | First Reading of Report |
| December 7, 2021 | Student Success Council | Approval of Report |
| December 8, 2021 | Classified Senate | Sharing of Report |
| December 9 2021 | Academic Senate | Sharing of Report |
| February 7, 2022 | Executive Leadership Team | Sharing of Report |
|  |  | 1st Reading 2nd Reading – Recommendation to _________ |
|  |  | 1st Reading 2nd Reading – Recommendation to _________ |
|  |  | 1st Reading 2nd Reading – Recommendation to _________ |

Standard Description of Project Stages

| Project Stages | Description |
| --- | --- |
| Initiation | Activities leading to the authorization and chartering of a project team |
| Preparation | Activities which occur once a team is authorized and can be conducted independently to plan, schedule, and setup the project (project management steps) |
| Team-Based Work | Activities which occur in a collaborative environment in which the project team works based on the scope of the charter |
| Formal Review | Activities by which deliverables are submitted to the sponsoring council for formal approval; may involve a sequence of governance review including ELT and/or other entities; formal review may result in acceptance of the deliverables; request for the project team to revisit the design/refinement stages; or abandonment of the project |
| Closure | Activities to celebrate the success of the project and archive the artifacts of the work completed |

Project Meeting Schedule:

2nd and 4th Wednesdays, from 2:00PM to 3:30PM

- Wednesday, September 15, 2:00PM to 3:30PM

- Wednesday, October 6, 2:00PM to 3:30PM

- Wednesday, October 20, 2:00PM to 3:30PM

- Wednesday, November 3, 2:00PM to 3:30PM – Review DRAFT Assessment and Recommendations

- Wednesday, November 17, 2:00PM to 3:30PM – Finalize DRAFT Assessment and Recommendations

PROJECT ORGANIZATION, ROLES, AND RESPONSIBILITIES

| Role | Responsibilities |
| --- | --- |
| Project Leads | - Prepares, leads, and follows up on meetings (see details of the Role of the Chair in the ARC Governance Framework) - Communicates the project to various stakeholders, and when appropriate, solicits feedback on draft deliverables through informal review processes - Submits the final deliverables to the sponsoring council for approval |
| Project Steward (may be one of the leads or a separate individual) | - Manages the project on behalf of the sponsoring council - Drafts the charter in consultation with the sponsoring council’s chairs - Conducts preliminary research to gather information on promising practices, product options, or other relevant materials to inform the project - Develops a work plan based on the charter to organize, sequence, and schedule the work of the project team within the available time frame - Reports progress to the sponsoring council - Maintains and archives project documentation at the conclusion of the project - Assists the project leads as needed |
| Team Members | - Participates in all project meetings and activities - Supplies valuable knowledge and perspective (often based on the individual’s responsibilities or role at ARC) - May be assigned specific project tasks to complete outside of project meetings - Assists with the “heavy lifting” that is required to accomplish the project deliverables |
| External Consultant (optional) | - Provides expertise and assistance from an external (non-ARC) perspective |
| Executive Sponsor (optional) | Large, high-impact projects only: - Champions the project from the executive level to secure buy-in and ensure viability - Communicates project purpose and vision - Allocates appropriate resources to support effective development, execution, and institutionalization - Maintains awareness of project status and helps mitigate risk - Mediates conflicts and facilitates dialogue to resolve project issues - Assumes other responsibilities as appropriate based on the project scope |

Please see Appendix A for a complete roster of the membership for each specified role.

PROJECT STAKEHOLDERS (Who has a vested interest in the project? Who will it impact?)

☒ Sponsoring Council 	☒ Project Team (including leads and members) 	              ☒ Project Steward

☒ Academic Senate	☒ Associated Student Body	☒ Classified Senate      ☒ PES	   ☐ Management beyond PES

☒ Instruction		☒ Student Services		☐ Administrative Services

☐ Specific departments or other entities:

COMMUNICATION PLAN (How will information be shared with the stakeholders?)

Based on the previously stated stakeholder list, the general plan for sharing project information is as follows:

| Communicated By | Audience | Frequency | Purpose |
| --- | --- | --- | --- |
| Project Steward | Sponsoring Council | Monthly | Regular update of project status |

Conflict Resolution

Any matter of significance which cannot be resolved by the project leads may be referred to the appropriate administrator (typically the chair of the sponsoring council) or to the President’s Executive Staff (PES).  Any significant change in charter scope will require approval of a revised charter by the Executive Leadership Team (ELT).

APPENDIX A: PROJECT MEMBERSHIP

| PROJECT TEAM |  |  |
| --- | --- | --- |
|  | Name of Participant | Role at the College |
| Project Co- Lead | Frank Kobayashi | Vice President of Instruction (Initial Implementation Team Member) |
| Project Co-Lead | Jeff Stephenson | Vice President of Student Services (Initial Implementation Team Member) |
| Members | Alisa Shubb | Academic Senate President(Initial Implementation Team Member) |
|  | Kristen Farlow | Classified Senate President |
|  | Student | Associated Students |
|  | Jennifer Laflam | Faculty (Initial Implementation Team Member) |
|  | Reyna Moore | Counselor (Initial Implementation Team Member) |
|  |  | Instructional Dean |
|  |  | Instructional Dean |
|  |  | Student Services Dean |
|  |  | Student Services Dean |
|  |  | Faculty Liaison |
|  |  | Faculty Liaison |
|  |  | HomeBase Staff |
|  |  | HomeBase Counselor |

| OTHER ROLES |  |
| --- | --- |
| Project Steward* |  |
| External Consultant(s) |  |
| Executive Sponsor (high-impact projects only) |  |

*May be one of the project leads or a separate individual

APPENDIX B: STUDENT PARTICIPATION

The student voice contributes a diverse perspective to ARC project teams and is highly valued.  As project teams have widely varied meeting schedules which can require a substantial time commitment, a flexible set of options have been defined to ensure that project dialogue and deliverables are influenced by the student perspective.

Please check one or more boxes below that indicate the methods the project lead/co-lead intend to use to facilitate student participation during this project.

|  | Method | Description | Compensated? |
| --- | --- | --- | --- |
| ☐ | ASB Appointment | Associated Student Body (ASB) appoints two students to serve on the project team and attend all meetings. This option is considered the standard method of representation. | Yes |
| ☐ | Student Resource Panel | In consultation with ASB, create a student resource panel that is called upon by the project lead/co-lead to provide student input at key points during the project. The resource panel may be an existing group of students (e.g., Sages) or a temporarily formed group assigned to the project. | Yes |
| ☐ | ASB Direct Involvement | Lead/co-leads work directly with ASB to be placed on an ASB agenda, present the project concept, and solicit input from students during a regularly scheduled ASB meeting. | No |
| ☐ | Student Survey or Focus Group | Project conducts a student survey or focus group through the Institutional Research Office and uses the results to inform the work of the project team. | No, but incentives may be provided on a case-by-case basis. |
| ☐ | Student Forum or Gallery Walk | Project holds a student forum or gallery walk during which large groups of students can provide input in response to narrative or visual prompts. ASB would be asked to assist in publicizing the date/time of the event to the student constituency. | No |
| ☐ | Other (please specify intended methods) |  |  |

Please see the “Governance: Student Compensation” document for further details on the compensation structure.